## Guidelines
Tab | Purpose
Guidelines | Provides general guidance on the content of each worksheet. The Testing Coordinator owns this document and ensures all worksheets are completed in full.
Change Info | Captures basic change information (e.g., project, service). It also records all ITSM/ITIL change records related to the testing\implementation. These records are accessible in the Testing Runbook and Backout Runbook tabs.
Contacts | Contains contact details for all Testing Team Members and the Command & Control group. Information entered here (e.g., role, team, initials) is used in the Roster, Testing Runbook, and Backout Runbook tabs.
Roster | Allows the Testing\Implementation Manager to create a visual representation of team members' availability and tasks, focusing only on Testing\Implementation Team members.
Testing Runbook | Details all tasks associated with testing integrations in Epic. Tip: To view only Dry Run information, filter column A.
Backout Runbook | Contains all tasks related to the backout process in case the change needs to be undone.
Issue Log | Records all issues during testing or backout. Issues include any material deviations from the documented tasks (e.g., changes to duration, tasks, or dependencies) and technical failures. If the forecast end time exceeds 1 hour, it must also be logged.
Doc Control | Provides version control, distribution list information, and Testing Plan approval details.
Dry Run | In dry runs, participants practice each step of the cutover plan that occurs in the days leading up to your go-live. Although you can't practice every nuance of a go-live, it is important to perform as many of the steps as possible, exactly as you will perform them in the days leading up to go-live. Develop a cutover plan and ensure that that all major players are aware of their go-live responsibilities.
Date of Issue
Issued By | Optimum Healthcare IT

## Summary
Applications | Total |  | Applications by Criticality |  |  | Cutover Dates
Testable | 49 |  | Criticality | Total |  | Prod | 2025-10-11
No Test System | 33 |  | 0 | 3 |  | Alt Prod | 2025-11-15
Post-Cutover Only | 21 |  | 1 | 31
Total Apps | 103 |  | 2 | 27
|  |  | 3 | 41
|  |  | 4 | 0
Weekly Passing Percentage
Week 1 - Pass | 20% |  | Current Application Testing Status
Week 2 - Pass | 31% |  | Pass | No Status | Fail
Week 3 - Pass | 84% |  | 41 | 0 | 8
|  |  | 83.67% | 0% | 16.33%
Testable | 38.83% |  |  | Peripherals Tested
No Test System | 63.11% |  |  | 100%
Prod Smoke Tests
90.48%
Criticality Stage | 0 | 1 | 2 | 3 | Total
Criticality Total | 3 | 31 | 27 | 42 | 103
Pass | 1 | 20 | 7 | 13 | 41
Fail | 0 | 2 | 2 | 4 | 8
Not Tested | 0 | 0 | 0 | 0 | 0
No Test System | 0 | 3 | 12 | 18 | 33
Post Cutover Test Only | 2 | 6 | 6 | 7 | 21
% Passed overall | 33.33% | 64.52% | 25.93% | 30.95% | 39.81%
% Passed testable | 100% | 90.91% | 77.78% | 76.47% | 83.67%


## Change Info
Business or Infrastructure Service Affected
Brief Description of Change
Project Name
Project Manager
Application Project Manager
Infrastructure Project Manager
Conference Call No.
Change Management Records
ITIL Change Record | Change Category | Status | Raised by | Actioned By | Description | Start Date | Start Time | End Date | End Time

## Contacts
Guidelines For Completion
The Organization, Task Owner (Name), Team, Role, and Dry Run 1-5 Status drop downs are driven from the Inputs worksheet.
Executive Steering Group (ESG) Members | [6 empty] | Contact Numbers(s)
Organization | Team | Role | Name | Location | Email | Home (Optional) | Business | Mobile
Application Testing Leads (ATL) | [6 empty] | Contact Numbers(s)
Organization | Team | Role | Name | Location | Email | Home (Optional) | Business | Mobile
NGHS | ECSA | ECSA | Steve Reagan
Testing Team Members (TTM) | [6 empty] | Contact Numbers(s)
Organization | Team | Role | Name | Location | Email | Home (?) | Business | Mobile
Epic | Technical Coordinator | Technical Coordinator | Test User
IT Service Delivery / IT Operations Group
Organization | Team | Group Mailbox | Landline
Change Management
Incident Management
Change Management
Incident Management
24*7 Operations Center

## Roster
|  |  | Guidelines For Completion |  |  | The roster is designed to visually track the Testing Team Members schedules, with role and name automatically populated from the Inputs sheet.
The start date and time should be entered in the designated cell to update the schedule.
The default duration is 12 hours, but this can be extended as needed, ensuring formulas are updated accordingly. and extending rows.
The schedule is presented in 1-hour blocks for clear visualization of team member availability.
Testing Start Date & Time | 2025-05-01 12:00
Role | Name | 45778.5 | 45778.5417 | 45778.5833 | 45778.625 | 45778.6667 | 45778.7083 | 45778.75 | 45778.7917 | 45778.8333 | 45778.875 | 45778.9167 | 45778.9583
Technical Coordinator | Test User
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0

## 3rd Party Testing Runbook
Testing Runbook
2025-05-01 12:00 | [5 empty] | Application |  |  | Resources | [9 empty] | Additional Info
Task ID | E0E- NP | E0A- NP | FDI- NP | AIP- NP | FHIR Override | System / Vendor | Testing Method / Steps Completed | Manager | Task Owner | Team | Flow | TST DryRun Capable? | Non-Prod Dry Run 1 Status | Non-Prod Dry Run 2 Status | Emergency Valid(8/4) | Cloud Prod Smoke Test Status | Criticality | Corepoint + IC | Task Notes | Cutover during testing window
1.2 | [5 empty] | Imprivata Badge Tap- Test Badge Tap |  | Scott Sanderson | Christopher Crisson | Client Engineering - Citrix |  | No | Not Testable | Not Testable | Not Testable | Pass | 0 | No | Only used on thin clients, so won't be able to test as part of phase1 Were successful in the Lab and in the clinic pilot. | Yes
1.69 | [5 empty] | Imprivata IDG | Interdisciplinary Group- FHIRInterconnect FHIR - Interconnect-IdG-TST | Donnie Lee | Pam Shelton | INFO SEC / ECSA | On-Prem Only Communication | Yes | Pass | Pass | Pass | Post Cutover Test Only | 0 | No | Per SailPoint: The bridge points to DNS names and if those are remaining the same, then there should be no issues. The ports that IGA uses are: IIS port 80 or 8080 Jetty port 8443 SQL port 1433 Test interface is VAL, so we'll need to test this post cutover. Low risk since we have a manual fallback process that is solid. | No
1.7 | [5 empty] | Imprivata ConfirmID | Interconnect | Donnie Lee | Manuel Bonilla-Pamela Shelton | ITS INFORMATION SECURITY | External via Internet | Yes | Pass | Pass | Pass | Post Cutover Test Only | 0 | Yes | Per SailPoint: The bridge points to DNS names and if those are remaining the same, then there should be no issues. The ports that IGA uses are: IIS port 80 or 8080 Jetty port 8443 SQL port 1433 Test interface is VAL, so we'll need to test this post cutover. Low risk since we have a manual fallback process that is solid. | No
1.17 | None | None | None | None |  | Aqure (Radiometer America) - Interface Engine | work with Respiratory tech to test ABG device | Mitzi Donaldson | Domah | CAT INPATIENT | Other | Yes |  | Pass |  | Pass | 1 | Yes | Corepoint Interface. RAM checking with analysts for testing 9/15 Will validate post cutover! | No
1.19 | None | None | None | None |  | Breeze Suite - Interface Engine | work with diagnist techs to place orders in Breeze | Mitzi Donaldson | Domah | CAT INPATIENT | Other | Yes |  | Pass |  | Pass | 1 | Yes |  | No
1.23 | None | None | None | None |  | Capsule Technologies | must redirect Neuron on an Anesthesia device to the cloud - PRD Only | Nicola Baker-Camejo | Lissette Alonso | CAT Inpatient (Optesia) | Other | Yes | Pass |  |  | Pass | 1 | Yes | Vendor involvement to point to new AWS Epic TST server - Lissette can do this in server. Lisette testing connectivity test Confirmed vitals crossing after pointing to cloud environment. 9/25 | Yes
1.24 | N/A | N/A | N/A | N/A |  | Care Everywhere | I pulled up a patient that has links established with outside sources and requested an update. It updated to reflect today's date. I also confirmed that I could view a document previously pulled in from an outside source. | Chris Wright | Jennifer Bailey | INTERFACES | External via Internet | Yes | Pass | Pass | Pass | Post Cutover Test Only | 1 | Yes | 9/24 - Can only test net connections, any other testing would have to be done post cutover. - CH | No
1.29 | [5 empty] | Change Healthcare PACS | 1. Order placed in EPIC and arrived. 2. Does the order populate in CHC under scheduled? 3. Move the study to ended status in EPIC. 4. Import a JPEG image to the scheduled study from C:\blankimage for the order in question. Clear the QA and change the study to reviewed status. 5. Check for image link in EPIC. 6. Once the dication is complete in PowerScribe check for report to cross to PACS. 7. Once the report is addeded in PowerScribe. 8.Check to see if Addendum is available in PACS | Tina Chapman | Rick Edwards-Chris Chumbley-Brandi Smith | ANC RADIOLOGY | Other | Yes | Pass |  | Fail | Post Cutover Test Only | 1 | Yes | 9/24 - This one should be able to be tested. -CH | No
1.38 | [5 empty] | CredentialStream (Verity) | Corepoint | Tamara Bethel-Williams |  |  |  |  | No Test System | No Test System | No Test System | No Test System | 1
1.22 | [5 empty] | CAPSLink | Corepoint interface out of Epic to CAPSLink for TPN orders for CAPS to compound the bags for us | Cindy Sullivan | Nicole Benson | CAT PHARMACY | Other | Yes | Pass |  | Pass | Pass | 1 | Yes | TST Dry Run: Sent test order to CAPS and they verified they recieved order. There is no flow back to EPIC - only outgoing orders. - 8/25 NB PRD Smoke Test: Also passed as above - 9/11 NB | No
1.4 | N/A | N/A | N/A | N/A |  | Cupid XML to HL7 | Interconnect | Tina Chapman | Brittney Nix-Melissa Fontenot, Ashlee Shiffer | ANC CARDIOLOGY / ECSA | External via Internet | Yes | Fail | Pass | Pass | Post Cutover Test Only | 1 | Yes | accession # 5431 is not showing an order - hyperlinks still asking for credentials upon launching. Order issue with accession rectified and measurements were successfully transmitted-AS. That Cupid to XML is just a file share listener with a transform file that it looks at to process files. The instance is not up yet though because Patrick and Shawn are working through the error I'm getting on the AWE2 background IC servers. We would need to test this against a different file share structure though so it doesn't steal any files from the PRD file shares. ~ Steve Reagan | No
1.45 | None | 100014 | None | 640630 640631 |  | Emdeon / Change Healthcare - Revenue Cycle management | unknown ownership | Tamara Bethel-Williams | Erin Cordova (Brett Kennedy - backup) | REV PATIENT ACCESS | Other | Yes | Pass |  | Pass | Post Cutover Test Only | 1 | Yes | Emdeon is a part of change Healthcare. Emdeon is a comprehensive application designed to streamline and enhance healthcare transactions. It facilitates the efficient processing of electronic claims and provides robust solutions for pharmacies, laboratories, and healthcare providers to improve billing, claims management, and data exchange. | No
1.46 | None | None | None | None |  | Emporos/Merchantsoft | Cash registers for CAT Pharmacy | Cindy Sullivan | Nicole Benson-Meredith Rudeseal-Quentin Decker-Sarah Davis-Earl Turner-Maria Gray-Dawson Byrnes | CAT PHARMACY | External via Internet | No | Post Cutover Test Only | Post Cutover Test Only | Post Cutover Test Only | Post Cutover Test Only | 1 | Yes |  | No
1.59 | [5 empty] | GE Centricity Perinatal (CPN) | Perinatal monitoring and documentation URL for accessing fetal strips. | Cindy Sullivan | Rachel Medley | CAT INPATIENT | Other | Yes | Not Testable | Not Testable | Not Testable | No Test System | 1 | No | We are not able to test CPN until we are in PRD | No
1.75 | [5 empty] | Keriton | New app 3rd party vendor, need to investigate testing needs. Not in LeanIX. There is also an app on mobile devices. There is no weblink in Epic for this app. Only mobile app. Only Corepoint. | Cindy Sullivan | Rachel Medley | CAT INPATIENT | Other | Yes | Pass |  | Pass | No Test System | 1 | Yes | https://nghs.service-now.com/now/nav/ui/classic/params/target/pm_project.do%3Fsys_id%3Dbd114a661bc7bd10ab9aca22604bcb7a%26sysparm_stack%3D%26sysparm_view%3D this integration goes through Corepoint. Keriton does not have a dedicated test server. | No
1.28 | 101089 103536 | None | 100074 | None |  | Change Healthcare- Interconnect Interqual case management | Follow script linked here for testing: https://nghs.sharepoint.com/:x:/r/teams/PMO-EpicFeb2025/Shared%20Documents/General/4%20-%20Testing/Epic%20FEB%2025%20Applications%20Testing%20Toolkits/February%2025%20GC%20-%20Criteria%20Review%20-%20Utilization%20Review.xlsx?d=wdfac4ef949f5488390f24a0430415338&csf=1&web=1&e=wIOVJd | Tamara Bethel-Williams | Erin Cordova (Brett Kennedy - backup) | REV PATIENT ACCESS | External via Internet | Yes | Fail | Fail | Pass | Pass | 1 | Yes | Doesn't use IP whitelisting; uses geofencing for incoming traffic, and SMART FHIR URL to return info to Epic. Issue logged | No
1.87 | [5 empty] | Omnicell | corepoint interface | Cindy Sullivan | Earl Turner | Willow | Other | Yes | Pass |  | Pass | Pass | 1 | Yes | TST Dry Run: Was able to see orders cross to Omnicell IVX and Omnicell Omnicenter - NB PRD Smoke Test: Was able to see orders cross to Omnicell Omnicenter 9/11 and IVX 9/16 - NB | No
1.88 |  | 100033 |  |  |  | Onbase | On-prem document management | Michael McNeilly | Tyjuane Albright | REV HIM | On-Prem Only Communication | Yes | Pass |  | Pass | Fail | 1 | No | Refresh from OLDTST is forcing us to manually rebuild E0A and start over - TA 9/22 Onbase saying that it's not making back into our system, potentially firewall related - TA 9/26 | No
1.93 | [5 empty] | Phillips Pix IX Webviewer | Likely a corepoint connection | Cindy Sullivan | Peter Dcosta | CAT INPATIENT |  | No | No Test System | No Test System | No Test System | Post Cutover Test Only | 1 | Yes | unable to be tested in TST without significant support from vendor | No
1.33 | None | None | None | None |  | Corepoint | Point interface engine to AWS TST | Chris Wright | Ram | Interfaces | Other | Yes | Pass |  | Pass | Pass | 1 | Yes |  | No
1.94 | [5 empty] | PowerScribe | 1. Enter an order in EPIC and move to arrived. 2. Check Powerscribe to see if order is in Scheduled status. 3. move the study to ended status in EPIC. 4. Create a dictation in Powerscribe. 5. Check EPIC for a report. 6. Create an addendum in Powerscribe. 7. Check Epic for an addendum. Needs to be tested before this app co-travels to cloud as well as after | Tina Chapman | Rick Edwards-Chris Chumbley-Brandi Smith | Radiant | Other | Yes | Pass | Pass | Fail | Pass | 1 | Yes | PS states the information comes from and goes to Corepoint so Whitlisting EPIC cloud IP not in scope. Per request | No
1.36 | None | 100120 | None | 334830 334831 |  | CRA Health (previously Volpera)- | Enpoint to CRA Health for Mammograpy. It has an E0A and AIP. Conformed still in use by RAM. |  | Donna Winslow, Amanda Osbourne-Lisa Thomas | CAT AMBULATORY / ANC RADIOLOGY/ ECSA | Other | Yes | Fail |  | Pass | Fail | 1 | Yes | Used in Prod, trying to see from RAM if used in TST- FHIR interface still needs to be tested. 9/11/25 - not working in PRD Cloud Per Ram: "Steve needs to do some routing to make it work on AWS PRD." MRN 030002677, Tuesday (9/23) test and the calculation did not pass Still failing as of the morning of 9/26 -Donna | No
1.52 | [5 empty] | FastPass | HL7 | Antonio Davis | Paul Deleon | Physical Security | Other | Yes |  | Pass |  | Pass | 1 | Yes | ADT interface connected . sent ADT as well | No
1.64 | [5 empty] | Haiku/Canto | Interconnect mobile instance Test device authentication and functionality. This should be available for TST testing. | Mark Thomas | Amanda Osbourne-Lisa Thomas | CAT AMBULATORY | External via Internet | Yes | Fail | Pass | Pass | Pass | 1 | Yes | When attempting to log into Haiku app as FAMMD I got message, "Login Failure Communication with the server timed out. Seek assistance from an administrator if the problem persists. Code: TimedOut. | No
1.67 | [5 empty] | IBM Merge Cardio Web | Corepoint and Interconnect for Cupid | Tina Chapman | Brittney Nix-Melissa Fontenot | ANC CARDIOLOGY | Other | Yes | Fail | Fail | Fail | Pass | 1 | Yes | Issue logged | No
1.71 | [5 empty] | Insight RX- FHIR | inbound Interconnect; no changes needed on their side per Elliot at Insight RX - 5/13 NB | Cindy Sullivan | Nicole Benson-Meredith Rudeseal-Quentin Decker-Sarah Davis-Earl Turner-Maria Gray-Dawson Byrnes | CAT PHARMACY | External via Internet | Yes | Fail | Pass | Pass | Pass | 1 | Yes | Testing DryRun #1--504 Gateway Time-out Testing DryRun #2 - 404- File or directory not found - issue resolved and now working https://epic-test1.insight-rx.com/epic/launch/60ea535b-ddf1-4182-9de0-07bda81c7e1d PRD Smoke passed 9/23 - NB | No
1.77 |  | 100029 100030 100031 |  |  |  | LRS - VPSX | Epic Printing | Scott Sanderson | Steve Reagan | ECSA | On-Prem Only Communication | Yes | Pass |  | Pass | Pass | 1 | Yes |  | Yes
1.8 | [5 empty] | Merge Heartsuite (Mac Lab) | corepoint + inbound Interconnect HL7 for Cupid do not have any component of Merge in our images, so accessing XML file is main test here | Tina Chapman | Brittney Nix-Melissa Fontenot | ANC CARDIOLOGY | External via Internet | Yes | Fail |  | Pass | Pass | 1 | Yes | Issue logged with below details | No
1.81 | [5 empty] | Merge Cardio | corepoint + inbound Interconnect HL7 for Cupid Image links and measurement XML files | Tina Chapman | Brittney Nix-Melissa Fontenot | ANC CARDIOLOGY | On-Prem Only Communication | Yes | Fail | Fail | Pass | Pass | 1 | No | Orders, results, and study measurements were successful. Image links are prompting for user crednetials when they should be passed automatically. Also launches in MS Edge instead of IE. Accession # 5429 is shared with an xray exam and second attemt accession # 5431 is not showing an order - hyperlinks still asking for credentials upon launching. Order issue with accession rectified and measurements were successfully transmitted-AS | No
2.01 |  | 100046 |  |  |  | RightFax | Change EPR from pointing to TST server to the PRD server | Scott Sandersion | Kevin McBride-Steve Reagan | ECSA, SysAdmin, InfoSec, HIM, and app teams like Epic and Trace | On-Prem Only Communication | Yes | Fail | Pass | Pass | Pass | 1 | Yes | https://VMFSRFAXT.nghs.com/rightfax/api/epicjobtransfers, Steve Reagan to check with Brandon to setup some testing 9/15 Mitchell needs | No
2.02 |  | 100025 |  |  |  | Rover | 1) Steve & Scott add config to mobile | Kevin McNeil | Nelson Dowling | ANC LAB | External via Internet | Yes |  | Pass |  | Pass | 1 | Yes | Matt mentioned Rover issues, want to do more indepth testing. He will speak with Peter Decosta. Rover passed for Beaker. Just need CLINDOC. | No
2.06 | [5 empty] | ServiceNow | EasyButton | Jason Camp | Mitchell Hawes | ITS SERVICE NOW | On-Prem Only Communication | Yes | Pass |  | Pass | Pass | 1 | No | Matt Fowler is checking with Mitchell on this 9/15 AWS PRD is pointed to dev, prd is still pointed to SN prd
2.12 | [5 empty] | Varian | Can test Aria workflow in TST The Linear Accelerator from Varian, is an advanced radiotherapy system that opens up treatment options for some of the most complex cancers in areas such as the head and neck, lung, breast, abdomen and liver. | Mark Thomas | Amanda Osborne | AMB ONCOLOGY - RESEARCH | Other | Yes | Pass |  | Pass | Pass | 1 | Yes | RAM mentioned this will be tested on Tuesday 9/16 9/18/25 AO - Leslie Tran completed this today with Ram | No
2.15 | [5 empty] | Willlow Ambulatory | Issues running on Citrix, generally requires full desktop PCs otherwise peripherals | Mark Thomas | Earl Turner | Willow | On-Prem Only Communication | Yes | No Test System | No Test System | No Test System | Pass | 1 | No | Testing logging into Willow and verify HSW URL shows as cloud
1.12 | [5 empty] | 3M HIS Revenue Cycle Solutions (3M CodeFinder, C&RS, C&RS Plus, 360 Encompass System, Medicode) |  | Michael McNeilly | Kim Grandy | REV REVENUE CYCLE | On-Prem Only Communication | No | Fail | No Test System |  | No Test System | 2 | Yes | then talk to the Solventum cloud. Since the servers are not moving, there should be no changes required on our | No
1.21 | [5 empty] | BD Alaris Pumps | BD Alaris Pumps need IPs swung internally. Add this to cutover runbook and find owner. vmasalariscce01 - 172.16.74.144 - CCE TEST vmasalariscce03 - 172.16.74.146 - CCE PROD This is slated to go live on PRD two days (OCT14) after Cloud PRD is supposed to cutover. Nancy Stockslager PM | Cindy Sullivan | Rachel Medley | CAT INPATIENT | Other | Yes | Fail | No Test System | No Test System | No Test System | 2 | No | Did not pass 5/28 testing. Currently building, and not slated to go live until October so will not be able to be tested within our TST cycles | No
1.26 | None | None | None | 640677 640695 640697 640733 640672 |  | Cardinal Health | Willow Ambulatory supply manager. It used to be Mckesson supply manager. | Cindy Sullivan | Earl Turner | CAT PHARMACY | External via Internet | No | No Test System | No Test System | No Test System | No Test System | 2 | Yes | can't be tested in TST | No
1.35 | N/A | N/A | N/A | N/A |  | Cover My Meds- EPA | Interconnect | Cindy Sullivan | Earl Turner | Willow/ CAT AMBULATORY / ECSA | External via VPN | No | Fail | No Test System | No Test System | No Test System | 2 | Yes | can't be tested in TST, Willow ambulatory through VPN | No
1.42 | N/A | N/A | N/A | N/A |  | Cyracom - Interpreter Services (new integration) | Interconnect FHIR - no TST env! | Tamara Bethel-Williams | Brandi Gaskin-Erin Cordova-Joshua Small | REV PATIENT ACCESS |  | No | No Test System | No Test System | No Test System | No Test System | 2 | Yes | no test env for cyracom | No
1.44 |  | 640690 640682 640684 |  | 640682 640683 640684 640685 |  | Dr. First (Surescripts) | (Med history and Real Time Pharmacy Benefits) | Mark Thomas | Amanda Osbourne-Lisa Thomas | Cat Amb | External via Internet | Yes | Pass |  | Pass | Post Cutover Test Only | 2 | Yes | This can only be tested if we have available patient data that has been set up to be received by Dr. First. Can be moved back to testable if we refresh patient data. | No
1.43 | 102759 103105 | 105364 2106900301 | 36390 36391 36392 36393 | None |  | DAX Ambient Copilot- FHIR Integration (Nuance) | Interconnect, likely need to test on Hyperdrive and Haiku/Canto mobile device Link to video showing steps: https://nghs.sharepoint.com/sites/ITSTechnicalTraining/_layouts/15/stream.aspx?id=%2Fsites%2FITSTechnicalTraining%2FShared%20Documents%2FDAX%20Copilot%2FDAX%20Pre%20Training%20Intro%2EMP4&referrer=StreamWebApp%2EWeb&referrerScenario=AddressBarCopied%2Eview%2Ef468a639%2D0c59%2D448b%2D9885%2Da9bade8b3fa9 |  | Lisa Thomas, Christian Haygood | CAT Inpatient/CAT AMB | External via Internet | Yes | Fail | Pass | Fail | Fail | 2 | Yes | FHIR was not avail during first round of testing - Firewall updates made and should be ready to go for Rd2 Confirmed working in pre-test with Training Team, with troubleshooting being done with 404 with customize window 8/4 The customization window in DAX Copilot is not working. Got the protected E0E migrated, and progressed to a new error, but it is showing DAX now instead of Ambient - CH 9/26 | No
1.5 | [5 empty] | Experian (Credit Card Payment) | Payment Safe Page | Tamara Bethel-Williams | Brandi Gaskin, Pam Shifflett, Jennifer Horn, Courtney Bailey | Rev Patient Access |  | No | Fail | No Test System | No Test System | No Test System | 2 |  | can't be tested in TST, there is no testing URL and DB return traffic would come back on wpprod.nghs.com instead of smoke url wptst.nghs.com | No
1.51 | [5 empty] | Experian RTE | Corepoint | Tamara Bethel-Williams | Brandi Gaskin, Pam Shifflett, Jennifer Horn, Courtney Bailey | Rev Patient Access |  | No | No Test System | No Test System | No Test System | No Test System | 2 |  | can't be tested in TST | No
1.53 | [5 empty] | File Export or FEX | Interconnect. FEX EpicCare Inpatient. Export files from Epic | Mitzi Donaldson | Sabrina Broome | Bugsy/LTC | On-Prem Only Communication |  | No Test System | No Test System | No Test System | No Test System | 2 | Yes | Bugsy exports their infections and procedures to NHSN (National Healthcare Safety Network). However, it doesn't work in the TST environment for testing purposes | No
1.48 | [5 empty] | Ephiphany | Corepoint Interface | Tina Chapman | Brittney Nix-Melissa Fontenot | ANC CARDIOLOGY / Clin Informatics | On-Prem Only Communication | Yes | Fail | Pass |  | Pass | 2 | No | Orders and results successful. Image link is prompting for credentials, which is not suppsoed to happen. Should pass credentials automatically.-BG This is now fixed | No
1.54 | [5 empty] | Finthrive CRD (interconnect) / CRD - Rapid Retest |  | Michael McNeilly | Brenda Fons | REV Rev Cycle | Other | Yes | Fail | Not Testable |  | Post Cutover Test Only | 2 | Yes | Does not currenlty work in TST on prem. We do not use consitantly in TST and do not know when stopped working. Looks like TST was overrode with PRD build and I have corrected that. Seeing if can reestablish connection on prem. Might have to test in PRD. Case is logged with vendor. 6/18/2025 We will plan to test this once SUP is on the cloud. Have not been able to reestablish a connection in TST prem. Last case update FinThrive needed natted IPs. We normally would not test in TST, with SUP being the preferred testing environment for this application. | No
1.57 | [5 empty] | Gastro | External via VPN | Chris Wright | Katie Denning | Interfaces | Other | Yes |  | Pass |  | Pass | 2 | Yes | RAM said not needed because HL7 Corepoint | No
1.58 | [5 empty] | GE Airstrip- secure remote access to patient data | Interconnect-GEAirStrip20085-PRD - contact vendor to whitelist IPs | Cindy Sullivan | Peter Dcosta | CAT INPATIENT | External via Internet | No | Not Testable | Not Testable | Not Testable | No Test System | 2 | Yes | unable to be tested in TST without significant support from vendor. This presentation covers the technical kickoff for GE AirStrip at Hartford Hospital DCMU. https://nghs.sharepoint.com/teams/PMO-GEMonitorandTelemetry/Shared Documents/General/2 - Planning/AirStrip/GE_AirStrip Tech Kickoff Deck - NGHS.pptx?web=1&EntityRepresentationId=f336be3a-3814-42bf-ade4-85dbda56c135
1.73 |  | 100066 | 103536 100428 |  |  | Intrado (Televox) | REV PATIENT ACCESS SMS / Televox SMS used by Mychart -Interconnect | Tamara Bethel-Williams | Jennifer Horn, Brandi Gaskin | REV PATIENT ACCESS | External via Internet | Yes | Pass | Pass | Pass | Pass | 2 | Yes | Had Mitchell bring over EAF 1 but need to swing over FHIR url to test again. JD 9/24/2025 | No
1.74 | [5 empty] | Invita Medical Invita UDI |  | Nicola Baker-Camejo | Lissette Alonso | CAT INPATIENT |  | No | Not Testable | Not Testable |  | No Test System | 2 |  | can't be tested in TST
1.55 | [5 empty] | First Databank- Drug Database | inbound Interconnect | Cindy Sullivan | Earl Turner | CAT PHARMACY | Other | Yes | Pass |  | Pass | Pass | 2 | No |  | No
1.82 | [5 empty] | MoveIT | Co-traveller status has been put on HOLD | Chris Wright | Mark Pawloski, Benjamin Simmons | Data Services | Other | Yes | Pass | Pass |  | Post Cutover Test Only | 2 | No | RAM to each out to MoveIT team 9/15 - Need epic\prd mount point from Steve We were able to successfully validate this for TST, but for PRD we will need to validate post-cutover to ensure it is connected properly. The //PF/prodfiles will not be cutover until after go Live so we cannot test until then.
1.83 | [5 empty] | Murj SMART on FHIR | open.epic/Epic on FHIR App clicked Murj docket on patient Carolina Cupid, link opens browser with murj docket url, but I do not have amurj account. Email sent to murj to see if they saw my attempt to connect in their test environment - awaiting response | Mark Thomas | Christian Haygood | CAT AMB | External via Internet |  | Not Testable | Not Testable | Not Testable | No Test System | 2 | Yes | Not able to test without Murj involement. Murj team sent docket on Tuesday, but testing window was not open due to reschedule. Email sent to Murj team to assist 6/18 and follow up sent 6/19 with updated testing window, awaiting reply - hoping to recieve test docket from Murj this afternoon or 6/20 | No
1.89 | [5 empty] | Outgoing Document Interface | ODI queue Interconnect | Michael McNeilly | Ram Chimpudi | REV HIM | Other | Yes | Fail | Pass | Pass | Post Cutover Test Only | 2 | Yes | Ram worked on this one when we had issues on first dry run. | No
1.9 |  | 100043 100163 100164 |  |  |  | Outlook Epic Integration | Outlook Epic Integration was not affected by AWS cloud project- I confimed thebuild looks appropraite in TST. Bkg | Jason Camp / Tamara Bethel-Williams | Brandi Gaskin / Lecia Grunfelder | M365 / REV PATIENT ACCESS / CAT INPATIENT | External via Internet | Yes | No Test System |  | No Test System | No Test System | 2 | Yes |  | No
2 | [5 empty] | Real Time Prescription Benefits (SureScripts) | Interconnect | Cindy Sullivan | Nicole Benson-Meredith Rudeseal-Quentin Decker-Sarah Davis-Earl Turner-Maria Gray-Dawson Byrnes | CAT PHARMACY | External via Internet | No |  | Fail |  | Post Cutover Test Only | 2 | Yes | Still not working - turns out Surescripts also just moved to the cloud so that might be related. Earl to troubleshoot with Amanda - Issue logged. Can't put non prod Surescripts certificates on prod server to test. | No
1.62 |  |  | TST Dashboard - 30403003657 TST Patient Detail - 30403003655 |  |  | Glytec Glucommander- Diabetes care | Interconnect Testing. Open EPIC find patient on critical care unit and place DKA Insulin Infusion order. In Sidebar see the order displayed. Click the link to Glucommander should open the patient detail window and the order should cross in. | Cindy Sullivan | Marylynn O'Reilly - Josie Morris | CAT INPATIENT | External via Internet | Yes | Fail | Pass | Pass | Pass | 2 | Yes | Error Message - SmartClickV3 experienced an unexpected problem causing your login to fail. SmartClickV3 unexpected exception processing Landing page. Error: G-GC-S-1-000006. System.IO.DirectoryNotFoundException: Could not find a part of the path 'D:\inetpub\wwwroot\GSENT.1689-t01.glytecenterprise.com.3512\csharp\Glucommander\Views\SMARTonFHIR\Landing\LandingError.cshtml'. 8/6 - TST Passes after troubleshooting with vendor | No
2.04 |  |  |  | 640119 640731 |  | SEPA- Southeastern Pathology Reports | Southeastern Pathology Associates provides comprehensive pathology services, specializing in diagnostic testing. | Chris Wright | Katie Denning | Interfaces | Other | Yes |  | Pass |  | Pass | 2 | Yes | VPN connection through Corepoint | No
2.09 | [5 empty] | Surescripts E-Prescribe | 3rd Party Pharmacy integration. Sending prescriptions and pulling in fill information. | Cindy Sullivan | Earl Turner | CAT PHARMACY / ECSA | External via Internet | Yes | Fail | Fail | Pass | Post Cutover Test Only | 2 | Yes | "Attestation" still needed from NGHS IT to Surescripts. Attestation logged with Surescripts (6/9) Still not working - turns out Surescripts also just moved to the cloud so that might be related. Earl to troubleshoot with Amanda - Issue logged | No
1.85 | [5 empty] | Nuance Dragon Medical One | Active FHIR API in Vendor Services 5/28/25 - Tried onsite testing and the mic does not work to integrate directly with Epic. The mic will work to dictate to the box and then transition to Epic. 6/2/25 - Reviewed with Tomel and Krista. Unable to test on Epic Cloud TST app. Can only test Dragon on published apps at this time. | Mark Thomas | Amanda Osbourne-Lisa Thomas-Ashley Tipton | CAT AMBULATORY / CAT INPATIENT | External via Internet | Yes | Not Testable | Not Testable | Not Testable | Fail | 2 | Yes | Will be testing in the Lab 9/18 Lisa Thomas successful test in lab/thin client 9/18 Moving this back to fail due to build issues with the Easy Button not working. We're trying to move these records back in time to validate. - 9/25
1.91 |  | 27030 27032 27033 |  |  |  | Pecos (Dorothy/HomeHealth) | interconnect. The information obtained regarding PECOS enrollment status is completed via an Epic Batch Run. The batch job obtains a file from CMS and uploads that file to system. The batch gets the file from CMS, uploads it to our FTP, then uploads the file to system. Using the following file paths: Non PRD file path: \\nghs.com\epic\NonProd\Hospice\PECOS PRD file path: \\nghs.com\epic\Prod\Hospice\PECOS Verified with ECSA these file paths will not be affected. | Cindy Sullivan | Casey Barron / Mary Beth Cole | HOSPICE | External via Internet | Yes | Pass | Pass | Pass | Pass | 2 | Yes | Ran Batch Job: 315 - NGHS HSPC PECOS in Putty AWS TST Environment; Batch job ran successfully; validated PECOS enrollment status updated in Hospice Intake StoryBoard | No
1.11 |  | 33100 33101 | 100112 | 200400 30820040001 | No | 3M Core Grouper for Claims- Test running claims, check Interconnect trace viewer for errors. | 1. Accessed a claims WQ with Medicare claims 2. Refreshed claims with CGS error 3. Error cleared 210000003452 200000005582 Per Steve: No errors on the log | Michael McNeilly | Kim Grandy | REV REVENUE CYCLE | On-Prem Only Communication | Yes | Pass |  | Pass | Pass | 3 | Yes | 3M does not rely on whitelisting. per 3M, User traffic from Epic goes to the 360 Encompass Servers (on-prem), which | No
1.13 | None | 100013 | 100001 | None |  | ACR Care Select- Decision support for Radiology | 1. Open Ancillary Orders for the patient. 2. Place a new order for an in-scope radiology procedure. Fill out all required fields, including the ordering provider, procedure, and diagnosis. 3. Verify Record Decision Support Information? question appears but is not a hard stop 4. Skip the Decision Support question. 5. Sign order 6. Verify CareSelect BPA does not fire 7. VERIFY: The new order appears in chart review and on the Appt Desk - Orders tab. Likely covered in weblink testing automation, looks like the last weblink test against on-prem failed in late March however https://epic-cdsapi.careselect.org/bpa https://epic-test-cdsapi.careselect.org/bpa | Tina Chapman | Rick Edwards / Chris Chumbley | ANC RADIOLOGY | Other | Yes | Pass |  | Pass | Pass | 3 | Yes | ACR Care Select 5/14/2025 5/20/2025, (ACR Select "Care Select" is a weblink per Katy Gantt. The links do not look active. Reaching out to Katy Gantt for more feedback. 5-19-25 Meeting with Katy Gantt to understand the workflow. Ticket placed with Care Select and email chain going with our Account Rep. will not need to be whitelisted the Epic IPs as the messges are coming from corepoint. Definitely want to validate this one with the PRD link 9/11 Successfully tested in Cloud PRD pointing to 'Test' Careselect URL. Requested to have E0A [100013] updated to use the 'PRD' Careselect URL instead of 'Test' Careselect URL. Discussed with Steve, Matthew, Jason D., and Ram. Ram advised this change would not be possible due to InterConnect settings/dependencies. Will have revisit at cutover. | No
1.15 | 1501207 101229 | 100069 | 100317 100069 | None |  | AIDA Healthcare | FHIR - no whitelisting required | Cindy Sullivan | Shelvia Stewart | CAT INPATIENT | External via Internet | Yes | Fail | Pass | Pass | Pass | 3 | Yes | https://aida.com/service/test FHIR Intergration | No
1.18 | 103081 | None | None | None |  | Baby 360 by YoMingo | Inbound to Epic - analyst would likely need to point to cloud instance of Epic | Cindy Sullivan | Rachel Medley | CAT INPATIENT | External via Internet | Yes | Pass |  | Pass | Pass | 3 | Yes | YoMingo does not utilize IP whitelisting, so the app will not be impacted by this update. https://baby360.com/mobile-app/ - FHIR IC integration | No
1.31 | 640100 103204 | 100653 2100000146 33500000936 | 100653 100697 33500000936 | None |  | Clinical Skills/ClinicalKey | Practitioner.Read (STU3)- FHIR based app | John Hale / Cindy Sullivan | Kyle Hriczo, Shelvia Stewart | ADM GENERAL / CAT INPATIENT | External via Internet | Yes | Pass | Fail | Not Testable | Fail | 3 | Yes | FHIR was not avail during first round of testing - Issue logged https://apps.healthcare.elsevier.com/launch/clinicalkey https://apps.healthcare.elsevier.com/launch/clinicalSkillsProd https://apps.healthcare.elsevier.com/launch/clinicalkey-nursing 9/25 - Clinical Skills errors: "Unknown issuer: clinicalSkillsProd has no EHR configuration for https://wptst.nghs.com/fhir-tst/api/FHIR/DSTU2" | No
1.39 | None | None | None | None |  | CSI ANC LAB | VPN, ORU messages via corepoint | Kevin McNiel | Nelson Dowling-Darshna Patel | ANC LAB | External via VPN | Yes |  | Pass |  | Pass | 3 | Yes |  | No
1.47 | 101017 101018 101471 101017 101016 | 100047 |  |  |  | Epic Video Client | Telehealth- uses SMS Sync queue | Mark Thomas |  | Ambulatory Team | External via Internet | Yes |  |  |  | Fail | 3 | Yes | Steve reached out to Mychart team to inquire testing Unable to access backend menu/configs, chatting with epic for options We also must wait for patient data to be available before we can successfully test this Hannah needs to take a look at this - 9/25 There could be more ports that werent discovered if we're only resolving the workflows where we encounter this. Client, Provider, Mobile, Translator, Regular Web | No
1.56 | [5 empty] | Fuse/Signal Radiation Oncology | Fuse extracts data from Aria and it uses the data to track patient documentation, charges, etc in Aria. Fuse cranks out a report so that Rad Onc leadership can use to identify missing/incorrect charges, look at data insights Technically if Aria is working, Fuse should be working too. 052825 - Aria worked for Varian testing. Do not have a way to test just the Fuse report. |  | Amanda Osbourne-Lisa Thomas | CAT AMBULATORY | External via VPN | Yes | Pass |  | Pass | Fail | 3 | Yes | Listed as Corepoint in 3rd party, but is in fact interconnect and will need to be whitelisted! Unable to access backend menu/configs, chatting with epic for options | No
1.14 | N/A | N/A | N/A | N/A |  | Acumen - Fresenius medical Care |  |  |  |  | Other | No | No Test System | No Test System | No Test System | No Test System | 3 | Yes | Checking with Chris Wright. Chris and Katie said it's all kidney care that goes through Corepoint and doesn't need to be tested.
1.16 | None | None | None | 640422 640423 |  | Ambry HL7 | Corepoint HL7 ORM Inbound data feed Connect to Bridges in Epic, which sends to Interconnect | Kevin McNiel | Nelson Dowling | ANC LAB | External via VPN | Yes | Pass |  | Pass | Pass | 3 | Yes | Interfaces/Katie Denning can take this 5.5.25 | No
1.25 | None | None | None | 640121 |  | Carefeed | new horizons LTC, but CAT INPATIENT and ADM GENERAL do not know this application | Chris Wright | Katie Denning | INTERFACES | Other | Yes |  | Pass |  | Pass | 3 | Yes | Interfaces/Katie Denning can take this 5.5.25 CP_OB_Carefeed_ADT_File | No
1.27 | N/A | N/A | N/A | N/A |  | Carta Healthcare Cartographer | Does not need to be tested for this project. | Anil Gullapalli | Anil Gullapalli | Data Services | External via Internet | Yes | No Test System | No Test System | No Test System | No Test System | 3 | Yes | Per Anil, Does not need to be tested for this project
1.3 | 101080 | None | None | 640100 640102 |  | Ciox Healthsource | Clarity (ROI Vendor)- Test release of Information, have ECSA check trace viewer for errors. | Michael McNeilly | Drew Gardner | REV HIM / ECSA | External via Internet | Yes | No Test System |  | No Test System | No Test System | 3 | Yes | Drew checking with Kenny and Todd 9/15 Mistakenly set to PASS in non-prd, no test system so will need to be test cutover | No
1.32 | [5 empty] | Cognitive Computing Nebula | https://galaxy.epic.com/Redirect.aspx?DocumentID=100051721&PrefDocID=126443 Need to work with Hannah to get IPs whitelisted Part of epic, so not needed to test | Anil Gullapalli | Anil Gullapalli | Data Services / ODBA | Other | Yes | Post Cutover Test Only | Post Cutover Test Only | Post Cutover Test Only | Post Cutover Test Only | 3 | No | N/A part of back end services to Epic | No
1.34 | N/A | N/A | N/A | N/A |  | Cosmos | https://cosmos.epic.com/ | Anil Gullapalli | Mark Pawloski | Data Services | Other | No | Fail | Post Cutover Test Only | Post Cutover Test Only | Post Cutover Test Only | 3 | Yes | Cosmos is a dataset created in collaboration with a community of health systems using Epic and is designed to improve patient care. By combining their data, participating organizations and Epic can make new discoveries and advance medicine. Cosmos also powers tools at the point of care, providing insights to clinicians that are tailored to the patient in front of them. | No
1.37 | N/A | N/A | N/A | N/A |  | CRC- Payment Safe Page | this is for credit card payments, not Cancer Risk Calculator as previously indicated | Tamara Bethel-Williams | Brandi Gaskin-Erin Cordova-Joshua Small | Rev Patient Access | External via Internet | No | Fail | No Test System | No Test System | No Test System | 3 | Yes | CRC Payment Safe Experian Health is a specialized application designed to enhance financial transactions within the healthcare sector. Its primary function is to provide secure payment processing solutions, ensuring the confidentiality and integrity of sensitive financial information. Can't be tested in TST | No
1.41 | 102520 | None | None | None |  | Cures FHIR- 21st Cures Act | For testing FHIR connections, not required for this testing event! | Chris Wright | Katie Denning | INTERFACES | External via Internet | No | No Test System | No Test System | No Test System | No Test System | 3 | Yes | Chris Wright working on this. Not testable at this time. | No
1.49 | [5 empty] | E-Signature/Controlled Meds | Digital signing server | Cindy Sullivan | Nicole Benson-Meredith Rudeseal-Quentin Decker-Sarah Davis-Earl Turner-Maria Gray-Dawson Byrnes | CAT PHARMACY | On-Prem Only Communication | No | Post Cutover Test Only | Post Cutover Test Only | Post Cutover Test Only | Post Cutover Test Only | 3 | No | There is not a non-prod DSS server for testing controlled meds. Can't put non prod dss certs on production servers for testing. Post cutover only. | No
1.6 | [5 empty] | Get Well - Rounding and Video Client | Clinicians need real-time information to deliver the best patient care possible; leaders need intuitive analytic dashboards for managing operations; patients — and their families | Tamara Bethel-Williams | Brandi Gaskin, Erin Cordova | REV PATIENT ACCESS | External via VPN | Yes |  | Pass |  | No Test System | 3 | No | Goes through VPN
1.61 |  |  |  | 640320 640985 640987 |  | GRITS | Interconnect Bridges interface https://www.grits.state.ga.us/gritsws/client_Service Also covers: Interconnect-QVC-TST GRITS Enter/administer vax on tst patient Epic TST - verify can see in GRITS TST portal. Enter historical vax on GRITS tst patient, verify Epic pulls via VAX Query. 052825 - GRITS tst did not show vaccine entered from Epic TST | Mark Thomas | Amanda Osborne | CAT AMBULATORY | External via Internet | Yes | Fail | Pass | Pass | No Test System | 3 | Yes | Earl and Amanda B verified GRITS testing https://www.gritstest.state.ga.us/gritsws/client_Service?wsdl 9/15 - GRITS doesn't allow testing in a PRD environment/can check real patients when data is available | No
1.63 | [5 empty] | Guardian Fusion (Guardian Research Network GRN Data Connection) | Active API. Interconnect FHIR | Anil Gullapalli | Mark Pawloski | ITS DATA SERVICES |  | No | No Test System | No Test System | No Test System | No Test System | 3 |  | can't be tested in TST
1.65 | [5 empty] | Happy Together Integrations | Interconnect. Does it go through the VPN? We should follow up with Hannah on this one as well. Hannah says likely not VPN and instead through the Care Everywhere network. This is likely for support connective services. 5/28 - DId not see Care Everywhere connection Cloud TST | Mark Thomas | Amanda Osbourne-Lisa Thomas | CAT AMBULATORY | External via Internet | Yes | Fail | Pass | Pass | Post Cutover Test Only | 3 | Yes | a grouping within Care Everywhere. Can't put non prod care everywhere certs on the prod servers for testing this. Post Cutover only. | No
1.66 | [5 empty] | HCI Solutions- Medication Warning | Instance only in POC, potentially orphaned and needs to be cleaned up not as part of this initiative. | Cindy Sullivan | Nicole Benson-Meredith Rudeseal-Quentin Decker-Sarah Davis-Earl Turner-Maria Gray-Dawson Byrnes | CAT PHARMACY | Other | No | No Test System | No Test System | No Test System | No Test System | 3 | No | Only in POC | No
1.68 | [5 empty] | ICD- National Cardiovascular Data Registry | Instance only in POC, potentially orphaned and needs to be cleaned up not as part of this initiative. | Tina Chapman | Brittney Nix-Melissa Fontenot | ANC CARDIOLOGY | External via Internet | Yes | No Test System | No Test System | No Test System | No Test System | 3 | Yes |  | No
1.76 | [5 empty] | Kyruus | interconnect, gets schedule dates for a provider. FHIR API.Kyruus provided the following update: the Kyruus network team has confirmed that there are no integrations currently that would necessitate any updates for IP whitelisting. This work is all set to close. BKG. - search and schedule appt with Provider Backend system FHIR access essentially uses a generic service account to access data. As a result, it is not applicable for patient-facing use cases. | Tamara Bethel-Williams | Brandi Gaskin, Pam Shifflett, Jennifer Horn, Courtney Bailey | Rev Patient Access | Other | Yes | Pass |  | Pass | Post Cutover Test Only | 3 | Yes | E0E Backend System. Approved through Showroom. | No
1.78 | [5 empty] | MacroHelix | stand-alone service from McKesson for the 340B. It only works in PRD because it has to have eligible patients with eligible meds with eligible insurance to generate a flat file that they place on a SFTP server. Not sure if we "push" the file to McKesson from the SFTP or they "pull" the file. The way that MOVEit connects to MacroHelix is via a SFTP connection, it is logging into ftp.mhiapps.com. I can set up a quick job if you want to send a test file over if you need to, but I don't see that we have anything built to send from Epic Test to MacroHelix in MOVEIt. We do have some PRD jobs. MOVEit is currently having no problems getting into the folder structure where we pick up files from EPIC Test | Cindy Sullivan | Benjamin Simmons | BI |  | Yes | Post Cutover Test Only | Post Cutover Test Only | Post Cutover Test Only | Post Cutover Test Only | 3 | No
1.79 | [5 empty] | Mapquest | Test UC on my way workflow via MyChart TST to see Mapquest map | Mark Thomas | Amanda Osbourne | CAT - MYCHART | External via Internet | Yes | Pass | Pass | Pass | Pass | 3 | Yes | AWS 3 and AWS 4 successful (052825) 9/15/25 - Amanda O - need the MyChart patient available for PRD. Cannot make a new one. Can test when patient data is back in PRD. 9/24 Verified Mapquest map showed for UC On My Way workflow | No
1.84 |  | 100082 |  |  |  | NPLEx |  | Cindy Sullivan | Earl Turner | Willow Amb | External via Internet | No | No Test System | No Test System | No Test System | No Test System | 3 | Yes | can't be tested in TST
1.86 |  | 100081 |  | 640337 |  | Olympus KE- endoscopy |  | Leslie McClain / Nicola Baker-Camejo | Lissette Alonso | CAT INPATIENT | Other | Yes | Pass |  | Pass | Pass | 3 | Yes | Was able to see images from the image link successfully. Goes through Corepoint and IC | No
1.97 | [5 empty] | Qpath/Telexy | interface engine ADT corepoint will be pointed for TST (no vendor contact needed) Does PACS need to coordinate with this testing? Need traffic from AWS to interconnect into PACS. Q-path provides a complete workflow solution for point-of-care ultrasound to help manage credentialing, quality assurance, reporting, billing, storage, teaching, research, and more. | Mitzi Donaldson | Ashley Tipton | CAT INPATIENT | Other | Yes | Pass |  | Pass | Pass | 3 | Yes |  | No
1.92 | [5 empty] | Phillips G3 SleepWare | ORM/ORU corepoint. Verified with Zachary Delimitros (Sleep Lab manager) we are not using the interface to send reports from Sleepware back into Epic. | Mark Thomas | Amanda Osbourne-Lisa Thomas | CAT AMBULATORY | Other | No | No Test System | No Test System | No Test System | No Test System | 3 | No | We do not use this interface to send reports from Sleepware back into Epic. BUT we do pull patient name/MRN and NGHS employee names from Epic. | No
1.95 | [5 empty] | Press Ganey | token request with Press Ganey https://epic.pressganey.com/api/v1/oauth2/token 74.119.202.118,74.119.202.119 Not through Epic, so we'll need to contact Press Ganey | John Hale | Kyle Hriczo | ADM GENERAL |  | No | No Test System | No Test System | No Test System | No Test System | 3 | Yes | of the group, I have reached back out to ask about working on phase 2 portion which is moving corepoint to the | No
1.96 | [5 empty] | PRISM-Opthamology | GNC does not use this application | Mark Thomas | Amanda Osborne | CAT AMBULATORY | Other | No | No Test System | No Test System | No Test System | No Test System | 3 | No | not used | No
1.98 | [5 empty] | QRDA | The application serves as a tool for generating and processing Quality Reporting Document Architecture (QRDA) documents, specifically catering to the needs of the Centers for Medicare & Medicaid Services (CMS) | Frankie Grant | Shreya Kotak | Population Health | External via Internet | Yes |  | Pass |  | Pass | 3 | Yes |  | No
1.99 | [5 empty] | Quest- Beaker ANC LAB results |  | Kevin McNeil | Nelson Dowling | ANC LAB | Other | Yes | Fail | Pass | Pass | Pass | 3 | Yes | Ram will change endpoint and Steve will make sure queues are running. | No
2.03 |  | 200004 |  |  |  | Salucro Payment and Device Integration (MedEpay/Elavon) | Longstreet Clinic | Jaime Frost | Sheila Snyder | CAT PHARMACY | External via Internet | No | No Test System | No Test System | No Test System | No Test System | 3 | Yes | Not testable in TST. We'll need to engage Longstreet as well, since they're the ones that will need to run the actual transaction(s). So we'll need a bit of lead time to make sure they're prepared to help when we reach that point. | No
2.07 | [5 empty] | SOC Telemed | Used to be Corepoint but is now FHIR intergration | Mitzi Donaldson | Ashley Tipton | CAT INPATIENT | Other | Yes |  | Pass |  | Fail | 3 | Yes | Mostly working, but the expected data is not coming back into system from SOC -AT MD 9/25 | No
2.05 | [5 empty] | Seqster Health | Patient Facing FHIR Intergration. Medication.Read (R4) third party research site NGHS does not advertise, own, or support. Patients can go to it completely outside of us and sign us and it will link to their MyChart. The only thing we have ever done on it was allow the URL as safe. We cannot test it bc we would have to be a patient working with that outside research study. | Mark Thomas | Amanda Osborne | CAT AMBULATORY | External via Internet | No | No Test System | No Test System | No Test System | Post Cutover Test Only | 3 | Yes | FHIR integration that is patient facing. Uses open.id to authenticate to uses MyChart and then they allow access. | No
2.08 | [5 empty] | Steris SPM | Corepoint. Will not be ready as part of this testing event | Nicola Baker-Camejo | Lissette Alonso | CAT INPATIENT |  | No | Not Testable | No Test System |  | No Test System | 3 |  | can't be tested in TST | No
2.1 | [5 empty] | TerminalWorks UniTwain |  | Tamara Bethel-Williams | Brandi Gaskin, Pam Shifflett, Jennifer Horn | REV PATIENT ACCESS |  | Yes | Not Testable | No Test System | Not Testable | No Test System | 3 |  | Unitwain is surface tablets, we only have them deployed in the GSV ED right now, and we only have licenses for those deployed. We'll just need to coordinate a time with staff when one isnt in use.
2.11 |  |  | 100091 |  |  | Unite Us | Patient.Read https://uniteus.com/press/unite-us-launches-patent-pending-integration-between-ehrs-and-its-social-care-coordination-platform/ https://emr.auth.uniteustraining.com/auth/smartonfhir | Frankie Grant | Shreya Kotak | Pop Health | External via Internet | Yes |  | Pass |  | Pass | 3 | Yes | SMART on FHIR FDI Record, https://emr.auth.uniteus.io/ | No
2.13 | [5 empty] | Waystar |  | Tamara Bethel-Williams | Brandi Gaskin, Pam Shifflett, Jennifer Horn, Courtney Bailey | Rev Patient Access |  | No | Not Testable | Not Testable | Not Testable | No Test System | 3 |  | can't be tested in TST | No
Note on B5: Jason Deaver: Inbound Interconnect traffic.
Note on C5: Jason Deaver: Outbound Interconnect Traffic
Note on D5: Jason Deaver: Desktop Integration like a button that launches an interconnect integration.
Note on E5: Jason Deaver: Interface record needed to go from bridges to the engine.
Note on F5: Jason Deaver: Column not needed based on way we are testing at NGHS.
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Provide some detail about "What" or "How" you tested? Any additional testing details/tasks can go here. If you have these documented someplace else, please provide that reference here.
Note on Q5: Jason Deaver: Current cloud prod testing
Note on R5: Jason Deaver: Criticality: 0 most critical
Note on S5: Jason Deaver: Corepoint or Interconnect or it could use both.

## Peripheral Testing Runbook
Application | Peripherals needed with thin client [All machines enabled for both Epic and Network printing] | Location of test machine | Able to be tested in TST? | Tested by and Date | Cloud TST Pass/Fail | Tested by and Date | Cloud PRD Smoke Test Pass/Fail | Comments
Cadence | Document Scanner | Lab | Yes |  | Fail |  | Fail
| Label Printer (Patient) |  |  |  | Fail |  | Pass | We don't use a specialized label printer, but printed successfully to 1405-EPIC-PRINTER-4
| Signature pad |  | Yes |  | Fail |  | Pass
| Camera |  |  |  | Fail |  | Pass
| Credit Card |  | No |  | Fail |  | Post-Cutover | We received a pass on this with Chestnut pilot
| Ambir Scanner (ID card) |  |  |  | Fail |  | Fail | Same error as document scanner, but I believe our users are no longer using ambir scanners.
Grand Central | Document Scanner | Lab | Yes |  | Fail | 9/24/25; EKC | Fail | "Error! The remote server location was not set from either the location or the environment ID."
| Label Printer (Patient) |  |  |  | Fail | 9/24/25; EKC | Pass | We don't use a specialized label printer, but printed successfully to 1405-EPIC-PRINTER-4
| Signature pad |  | Yes |  | Fail | 9/24/25; EKC | Pass
| Camera |  | Yes |  | Fail | 9/24/25; EKC | Pass
| Credit Card |  | No |  | Fail |  | Post-Cutover | We received a pass on this with Chestnut pilot
| Ambir Scanner (ID card) |  |  |  | Fail | 9/24/25; EKC | Fail | Same error as document scanner, but I believe our users are no longer using ambir scanners.
Radiant | Document Scanner (fujitsu) | Lab | Yes | 2025-06-06 | Pass | 9/15/2025 CC,BS | Pass
| Document Scanner (canon) |  |  |  |  | 9/23/2025 CC, DK | Pass | Had to requisition one for the lab from our Field Services partners
| Document Printing (Mammography) |  |  |  |  | 9/23/2205 CC, DK | Fail | Can't find printers from PRD
| Barcode Scanner |  |  |  | Pass | 9/15/2025 CC,BS | Pass | Confirmed again on 9/23 Wireless scanner in the lab doesn't seem to scan
| Signature pad |  | Yes | 2025-06-06 | Pass | 9/15/2025 CC,BS | Pass | Epic can't connect, shows broken in image. Citrix team looking at. Pass 9/23
| Zebra Printer |  | Yes | 2025-06-06 | Pass | 9/15/2025 CC,BS | Fail | LWS default to down, enabling uncovered a new issue. Steve investigating. Still not available as of 9/23
Orders | Dragon Mic | Lab | Yes |  | Fail |  | Fail
ASAP | Dragon Mic | Lab | Yes |  | Fail |  | Fail | Buttons not available, likely due to OLDTST build/records not being up to date
| Barcode Scanner |  | Yes |  | Pass |  | Pass
| Document Scanner |  | Yes |  | Pass |  | Fail | Hyland server issue
| Zebra |  | Yes |  | Pass |  | Pass
Optesia | Barcode Scanner | Lab | Yes | 2025-06-19 | Pass |  | Pass
| Dragon Mic |  | Yes |  | Fail |  | Fail
| topaz signature pad |  | Yes | 2025-06-19 | Pass |  | Pass
| Badge Reader |  | Yes | 2025-06-19 | Pass |  | Pass
Cupid | Barcode Scanner | Lab |  | Melissa | Pass | 9/23/25 Nick | Pass | acc # 5832 (TST) , acc# 4848 (PRD)
| Desktop integration |  |  |  | Pass | 9/16/25 BG | Pass
| Mac Lab |  |  |  | Pass | 9/16/25 BG | Pass
| HeartSuite Hemo |  |  |  | Pass | 9/16/25 BG | Pass
| Epiphany |  |  |  | Pass | 9/16/25 BG | Pass
Beacon | Barcode Scanner | Lab | Yes |  | Pass | 9/25/25 LT | Pass
| Document Scanner |  | Yes |  | Pass | 9/25/25 LT | Fail
| Dragon Mic |  | Yes |  | Fail | 9/25/25 LT | Pass
ClinDoc | Barcode Scanner | Lab | Yes | 6/11/25 RM | Pass | 9/17/25 RM | Pass
| Zebra Printer |  | Yes | 6/11/25 RM | Pass | 9/17/25 RM | Fail
Stork | Barcode Scanner | Lab | Yes | 6/11/25 RM | Pass | 9/17/25 RM | Pass
| Zebra Printer |  | Yes | 6/11/25 RM | Pass | 9/17/25 RM | Fail
LTC | ClinDoc will test peripherals for LTC | Lab | Yes | 6/11/25 RM | Pass | 9/17/25 RM | Fail
Ambulatory | Dragon Mic | Lab | Yes | 6/19/25 LT | Pass | 9/25/25 LT | Pass | successful test on thin client 9/18
| Barcode scanning |  |  |  | Pass | 9/25/25 LT | Pass | Works on TST, silently fails on PRD LT 9/18/25 Reaching out to citrix team
| Label Printing |  |  |  |  | 9/25/25 LT | Fail | Same issues as others LT 9/18/25
| Docment Printing |  |  |  |  | 9/25/25 LT | Pass
| Document Scanner |  | Yes | 6/19/25 LT | Pass | 9/25/25 LT | Fail | Same issues as others LT 9/18/25
Hospice | Barcode Scanner, Zebra Printer, Label Printer (Patient) | Lab | Yes | 6/19/25 CB | Pass |  | Pass | ClinDoc covers Hospice
Willow IP | Label Printer (Meds) | Lab | Yes | 6/19/2025 NB | Pass | 9/16/25 NB | Pass | and tested printing to Xerox - All passed 9/25/25 NB
| Barcode Scanner (Meds) |  | Yes | 6/19/2025 NB | Pass | 9/9/25 NB | Pass
Willow OP | Label Printer (Meds) | Lab |  |  | Pass |  | Pass
| Scanner (Prescription) | [5 empty] | Pass
Beaker | Zebra Printer | Lab | Yes |  | Pass |  | Pass
| Barcode Scanner |  | Yes |  | Pass |  | Pass
| Rover (iOS and Android) |  | Yes |  | Pass |  | Pass
Ambulatory/MyChart | Haiku | Lab | Yes | 2025-06-19 | Pass | 9/25/25 LT | Pass
| Canto | Lab | Yes | 2025-06-19 | Pass | 9/25/25 LT | Pass
ClinDoc | iPad | [5 empty] | Pass
HIM | ROI & Utility client |  | Yes | 6/17/2025 Ty. A | Pass | 9/9/25 TA | Fail | Working with Vendors (epic and onbase)

## Epic Build Smoke Test
Team | Pass/Fail | Notes
Cadence | Pass | Created and scheduled test pt MRN: 012498562 within AWS PRD Smoke Test EVN- bkg
Grand Central | Pass | 9/24/25 EKC
Radiant | Pass | 9/11/25 CHC
Orders | Pass | 9/23/25 KT
ASAP | Pass | 9/17/25 AT
Optesia | Pass | 09/17/25 LA (3rd party apps impacted by FHIR not tested)
Cupid | Pass | 9/9/25 AMS/MF tested MRN 012498558 acc# 22265802
Beacon | Pass | 9/23/25 AO
ClinDoc |  | Will be completed 9/26 PD
Stork | Pass
Ambulatory | Pass | 9/9/25 AO
Hospice | Pass | Covered by inpatient 9/25/25 MBC
Willow IP | Pass | 9/17/25 NB
Willow OP | Pass | 9/18/25 ET
Beaker | Pass | 9/12/25 NBD
Ambulatory/MyChart | Pass | 9/23/25 AO
Prelude | Pass | 9/25/25 EKC
HIM | Fail | EPIC does not communicate with the OnBase server. I updated the FDI record and E0A in EPIC, along with the OnBase config files on the Citrix server, with the new EPIC environment ID. I have an SLG with EPIC and a ticket open with OnBase. Epic is unable to open the 3M Encoder with the FHIR error. These errors are also being seen elsewhere.
Longstreet | Pass | Working with Heidi Pritchett and Ty Nguyen
GNC |  | Working with Staci Berry
Resolute (HB/PB) | Fail | PB/HB smoke testing passes with the exception of Rapid Retest and 3M. Rapid Retest will not be tested until cutover.
Beaker
Radiant

## Test Patient claim
Claimed | Last Name | First Name | Middle Name | Suffix | Sex | Gender Identity | Sexual Orientation | Sex Assigned At Birth | DOB | SSN | Street Address Line 1 | Street Address Line 2 | City | State | Zip Code | Country | County | House Number | District | Home Phone | Work Phone | Cell Phone | Race | Language | Religion | Ethnicity | Marital Status | Email Address
| ZZTESTLASTNAME | TESTFIRSTNAME | TESTMIDDLENAME | JR | F |  |  |  | ######## | 999-99-9999 | 123 Oak Street | Apt 4 | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6080000000 | ASIAN | English | Other | Caucasian | Single | email@noemail.com
| INTRoundOne | One |  |  | M |  |  |  | ######## | 111-11-1111 | 124 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | Two |  |  | F |  |  |  | ######## | 111-11-1112 | 125 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | Three |  |  | M |  |  |  | ######## | 111-11-1113 | 126 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | Four |  |  | F |  |  |  | ######## | 111-11-1114 | 127 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
Nicole Benson | INTRoundOne | Five |  |  | M |  |  |  | ######## | 111-11-1115 | 128 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | Six |  |  | F |  |  |  | 1965-08-08 | 111-11-1116 | 129 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | Seven |  |  | M |  |  |  | ######## | 111-11-1117 | 130 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
Rachel Medley | INTRoundOne | Eight |  |  | F |  |  |  | ######## | 111-11-1118 | 131 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | Nine |  |  | M |  |  |  | ######## | 111-11-1119 | 132 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | Ten |  |  | F |  |  |  | 1969-01-01 | 111-11-1120 | 133 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
Josie Morris | INTRoundOne | Eleven |  |  | M |  |  |  | 1969-08-07 | 111-11-1121 | 134 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | Twelve |  |  | F |  |  |  | ######## | 111-11-1122 | 135 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | Thirteen |  |  | M |  |  |  | ######## | 111-11-1123 | 136 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
Ashlee Shiffer | INTRoundOne | Fourteen |  |  | F |  |  |  | ######## | 111-11-1124 | 137 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | Fifteen |  |  | M |  |  |  | ######## | 111-11-1125 | 138 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | Sixteen |  |  | F |  |  |  | ######## | 111-11-1126 | 139 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | Seventeen |  |  | M |  |  |  | ######## | 111-11-1127 | 140 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | Eighteen |  |  | F |  |  |  | 1985-03-02 | 111-11-1128 | 141 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | Nineteen |  |  | M |  |  |  | ######## | 111-11-1129 | 142 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | Twenty |  |  | F |  |  |  | ######## | 111-11-1130 | 143 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | TwentyOne |  |  | M |  |  |  | ######## | 111-11-1131 | 144 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | TwentyTwo |  |  | F |  |  |  | 1988-09-03 | 111-11-1132 | 145 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | TwentyThree |  |  | M |  |  |  | ######## | 111-11-1133 | 146 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | TwentyFour |  |  | F |  |  |  | ######## | 111-11-1134 | 147 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | TwentyFive |  |  | M |  |  |  | ######## | 111-11-1135 | 148 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | TwentySix |  |  | F |  |  |  | 1963-01-06 | 111-11-1136 | 149 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | TwentySeven |  |  | M |  |  |  | ######## | 111-11-1137 | 150 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | TwentyEight |  |  | F |  |  |  | ######## | 111-11-1138 | 151 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | TwentyNine |  |  | M |  |  |  | 1964-09-01 | 111-11-1139 | 152 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | Thirty |  |  | F |  |  |  | ######## | 111-11-1140 | 153 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | ThirtyOne |  |  | M |  |  |  | ######## | 111-11-1141 | 154 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | ThirtyTwo |  |  | F |  |  |  | ######## | 111-11-1142 | 155 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | ThirtyThree |  |  | M |  |  |  | 1966-06-09 | 111-11-1143 | 156 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | ThirtyFour |  |  | F |  |  |  | 1967-05-05 | 111-11-1144 | 157 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | ThirtyFive |  |  | M |  |  |  | 1967-05-06 | 111-11-1145 | 158 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | ThirtySix |  |  | F |  |  |  | ######## | 111-11-1146 | 159 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | ThirtySeven |  |  | M |  |  |  | ######## | 111-11-1147 | 160 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | ThirtyEight |  |  | F |  |  |  | ######## | 111-11-1148 | 161 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | ThirtyNine |  |  | M |  |  |  | ######## | 111-11-1149 | 162 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | Forty |  |  | F |  |  |  | ######## | 111-11-1150 | 163 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | FortyOne |  |  | M |  |  |  | ######## | 111-11-1151 | 164 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | FortyTwo |  |  | F |  |  |  | ######## | 111-11-1152 | 165 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | FortyThree |  |  | M |  |  |  | ######## | 111-11-1153 | 166 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | FortyFour |  |  | F |  |  |  | 1978-02-09 | 111-11-1154 | 167 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | FortyFive |  |  | M |  |  |  | ######## | 111-11-1155 | 168 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | FortySix |  |  | F |  |  |  | ######## | 111-11-1156 | 169 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | FortySeven |  |  | M |  |  |  | 1966-01-03 | 111-11-1157 | 170 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | FortyEight |  |  | F |  |  |  | ######## | 111-11-1158 | 171 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | FortyNine |  |  | M |  |  |  | ######## | 111-11-1159 | 172 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | Fifty |  |  | F |  |  |  | ######## | 111-11-1160 | 173 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | FiftyOne |  |  | M |  |  |  | 1967-05-05 | 111-11-1161 | 174 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | FiftyTwo |  |  | F |  |  |  | ######## | 111-11-1162 | 175 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | FiftyThree |  |  | M |  |  |  | 1968-06-09 | 111-11-1163 | 176 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | FiftyFour |  |  | F |  |  |  | ######## | 111-11-1164 | 177 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | FiftyFive |  |  | M |  |  |  | ######## | 111-11-1165 | 178 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | FiftySix |  |  | F |  |  |  | ######## | 111-11-1166 | 179 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | FiftySeven |  |  | M |  |  |  | ######## | 111-11-1167 | 180 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | FiftyEight |  |  | F |  |  |  | ######## | 111-11-1168 | 181 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | FiftyNine |  |  | M |  |  |  | ######## | 111-11-1169 | 182 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | Sixty |  |  | F |  |  |  | ######## | 111-11-1170 | 183 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | SixtyOne |  |  | M |  |  |  | ######## | 111-11-1171 | 184 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | SixtyTwo |  |  | F |  |  |  | ######## | 111-11-1172 | 185 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | SixtyThree |  |  | M |  |  |  | ######## | 111-11-1173 | 186 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | SixtyFour |  |  | F |  |  |  | ######## | 111-11-1174 | 187 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | SixtyFive |  |  | M |  |  |  | ######## | 111-11-1175 | 188 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | SixtySix |  |  | F |  |  |  | ######## | 111-11-1176 | 189 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | SixtySeven |  |  | M |  |  |  | 1977-01-07 | 111-11-1177 | 190 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | SixtyEight |  |  | F |  |  |  | 1978-06-04 | 111-11-1178 | 191 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | SixtyNine |  |  | M |  |  |  | ######## | 111-11-1179 | 192 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | Seventy |  |  | F |  |  |  | ######## | 111-11-1180 | 193 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | SeventyOne |  |  | M |  |  |  | ######## | 111-11-1181 | 194 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | SeventyTwo |  |  | F |  |  |  | ######## | 111-11-1182 | 195 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | SeventyThree |  |  | M |  |  |  | 1965-08-09 | 111-11-1183 | 196 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | SeventyFour |  |  | F |  |  |  | ######## | 111-11-1184 | 197 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | SeventyFive |  |  | M |  |  |  | ######## | 111-11-1185 | 198 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | SeventySix |  |  | F |  |  |  | ######## | 111-11-1186 | 199 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | SeventySeven |  |  | M |  |  |  | ######## | 111-11-1187 | 200 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | SeventyEight |  |  | F |  |  |  | ######## | 111-11-1188 | 201 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | SeventyNine |  |  | M |  |  |  | ######## | 111-11-1189 | 202 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | Eighty |  |  | F |  |  |  | 1969-05-09 | 111-11-1190 | 203 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | EightyOne |  |  | M |  |  |  | ######## | 111-11-1191 | 204 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | EightyTwo |  |  | F |  |  |  | ######## | 111-11-1192 | 205 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | EightyThree |  |  | M |  |  |  | ######## | 111-11-1193 | 206 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | EightyFour |  |  | F |  |  |  | ######## | 111-11-1194 | 207 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | EightyFive |  |  | M |  |  |  | ######## | 111-11-1195 | 208 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | EightySix |  |  | F |  |  |  | ######## | 111-11-1196 | 209 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | EightySeven |  |  | M |  |  |  | ######## | 111-11-1197 | 210 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | EightyEight |  |  | F |  |  |  | ######## | 111-11-1198 | 211 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | EightyNine |  |  | M |  |  |  | 1976-07-08 | 111-11-1199 | 212 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | Ninety |  |  | F |  |  |  | ######## | 111-11-1200 | 213 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | NinetyOne |  |  | M |  |  |  | ######## | 111-11-1201 | 214 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | NinetyTwo |  |  | F |  |  |  | ######## | 111-11-1202 | 215 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | NinetyThree |  |  | M |  |  |  | ######## | 111-11-1203 | 216 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | NinetyFour |  |  | F |  |  |  | ######## | 111-11-1204 | 217 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | NinetyFive |  |  | M |  |  |  | 1979-09-03 | 111-11-1205 | 218 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | NinetySix |  |  | F |  |  |  | ######## | 111-11-1206 | 219 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | NinetySeven |  |  | M |  |  |  | ######## | 111-11-1207 | 220 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | NinetyEight |  |  | F |  |  |  | ######## | 111-11-1208 | 221 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | NinetyNine |  |  | M |  |  |  | ######## | 111-11-1209 | 222 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | OneHundred |  |  | F |  |  |  | 1966-03-03 | 111-11-1210 | 223 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | OneHundredOne |  |  | F |  |  |  | 1967-06-05 | 111-11-1211 | 224 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | OneHundredTwo |  |  | M |  |  |  | ######## | 111-11-1212 | 225 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | OneHundredThree |  |  | M |  |  |  | ######## | 111-11-1213 | 226 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | OneHundredFour |  |  | F |  |  |  | ######## | 111-11-1214 | 227 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | OneHundredFive |  |  | M |  |  |  | ######## | 111-11-1215 | 228 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | OneHundredSix |  |  | F |  |  |  | ######## | 111-11-1216 | 229 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | OneHundredSeven |  |  | M |  |  |  | ######## | 111-11-1217 | 230 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | OneHundredEight |  |  | F |  |  |  | ######## | 111-11-1218 | 231 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | OneHundredNine |  |  | M |  |  |  | ######## | 111-11-1219 | 232 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | OneHundredTen |  |  | F |  |  |  | ######## | 111-11-1220 | 233 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | OneHundredEleven |  |  | M |  |  |  | ######## | 111-11-1221 | 234 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | OneHundredTwelve |  |  | F |  |  |  | ######## | 111-11-1222 | 235 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | OneHundredThirteen |  |  | M |  |  |  | ######## | 111-11-1223 | 236 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | OneHundredFourteen |  |  | F |  |  |  | ######## | 111-11-1224 | 237 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | OneHundredFifteen |  |  | M |  |  |  | ######## | 111-11-1225 | 238 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | OneHundredSixteen |  |  | F |  |  |  | 1978-01-02 | 111-11-1226 | 239 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | OneHundredSeventeen |  |  | M |  |  |  | ######## | 111-11-1227 | 240 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | OneHundredEighteen |  |  | F |  |  |  | ######## | 111-11-1228 | 241 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | OneHundredNineteen |  |  | M |  |  |  | ######## | 111-11-1229 | 242 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | OneHundredTwenty |  |  | F |  |  |  | ######## | 111-11-1230 | 243 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | OneHundredTwentyOne |  |  | M |  |  |  | ######## | 111-11-1231 | 244 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | EndtoEndOne |  |  | F |  |  |  | ######## | 111-11-1232 | 245 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | EndtoEndTwo |  |  | M |  |  |  | ######## | 111-11-1233 | 246 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | EndtoEndThree |  |  | F |  |  |  | ######## | 111-11-1234 | 247 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | EndtoEndFour |  |  | M |  |  |  | ######## | 111-11-1235 | 248 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | EndtoEndFive |  |  | F |  |  |  | 1968-05-02 | 111-11-1236 | 249 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | EndtoEndSix |  |  | M |  |  |  | ######## | 111-11-1237 | 250 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | EndtoEndSeven |  |  | F |  |  |  | ######## | 111-11-1238 | 251 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | EndtoEndEight |  |  | M |  |  |  | ######## | 111-11-1239 | 252 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | EndtoEndNine |  |  | F |  |  |  | ######## | 111-11-1240 | 253 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | EndtoEndTen |  |  | M |  |  |  | ######## | 111-11-1241 | 254 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | PMOne |  |  | F |  |  |  | ######## | 111-11-1242 | 255 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | PMTwo |  |  | M |  |  |  | ######## | 111-11-1243 | 256 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | PMThree |  |  | F |  |  |  | 1974-08-01 | 111-11-1244 | 257 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | PMFour |  |  | M |  |  |  | ######## | 111-11-1245 | 258 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | PMFive |  |  | F |  |  |  | ######## | 111-11-1246 | 259 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | PMSix |  |  | M |  |  |  | ######## | 111-11-1247 | 260 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | PMSeven |  |  | F |  |  |  | ######## | 111-11-1248 | 261 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | PMEight |  |  | M |  |  |  | ######## | 111-11-1249 | 262 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | PMNine |  |  | F |  |  |  | ######## | 111-11-1250 | 263 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | PMTen |  |  | M |  |  |  | ######## | 111-11-1251 | 264 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | PMEleven |  |  | F |  |  |  | ######## | 111-11-1252 | 265 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | PMTwelve |  |  | M |  |  |  | ######## | 111-11-1253 | 266 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | PMThirteen |  |  | F |  |  |  | ######## | 111-11-1254 | 267 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | PMFourteen |  |  | M |  |  |  | 1980-04-02 | 111-11-1255 | 268 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | PMFifteen |  |  | F |  |  |  | ######## | 111-11-1256 | 269 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| INTRoundOne | PMSixteen |  |  | M |  |  |  | ######## | 111-11-1257 | 270 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| INTRoundOne | PMSeventeen |  |  | F |  |  |  | ######## | 111-11-1258 | 271 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BCNOne |  |  | M |  |  |  | ######## | 111-11-1259 | 272 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BCNTwo |  |  | F |  |  |  | ######## | 111-11-1260 | 273 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BCNThree |  |  | M |  |  |  | ######## | 111-11-1261 | 274 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BCNFour |  |  | F |  |  |  | 1980-04-02 | 111-11-1262 | 275 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BCNFive |  |  | M |  |  |  | ######## | 111-11-1263 | 276 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BCNSix |  |  | F |  |  |  | ######## | 111-11-1264 | 277 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BCNSeven |  |  | M |  |  |  | ######## | 111-11-1265 | 278 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BCNEight |  |  | F |  |  |  | ######## | 111-11-1266 | 279 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BCNNine |  |  | M |  |  |  | ######## | 111-11-1267 | 280 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BCNTen |  |  | F |  |  |  | ######## | 111-11-1268 | 281 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BCNEleven |  |  | M |  |  |  | 1980-04-02 | 111-11-1269 | 282 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BCNTwelve |  |  | F |  |  |  | ######## | 111-11-1270 | 283 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BCNThirteen |  |  | M |  |  |  | ######## | 111-11-1271 | 284 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BCNFourteen |  |  | F |  |  |  | ######## | 111-11-1272 | 285 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BCNFifteen |  |  | M |  |  |  | ######## | 111-11-1273 | 286 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BCNSixteen |  |  | F |  |  |  | ######## | 111-11-1274 | 287 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BCNSeventeen |  |  | M |  |  |  | ######## | 111-11-1275 | 288 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BCNEighteen |  |  | F |  |  |  | 1980-04-02 | 111-11-1276 | 289 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BCNNineteen |  |  | M |  |  |  | ######## | 111-11-1277 | 290 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BCNTwenty |  |  | F |  |  |  | ######## | 111-11-1278 | 291 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BCNTwentyOne |  |  | M |  |  |  | ######## | 111-11-1279 | 292 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BCNTwentyTwo |  |  | F |  |  |  | ######## | 111-11-1280 | 293 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BCNTwentyThree |  |  | M |  |  |  | ######## | 111-11-1281 | 294 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BCNTwentyFour |  |  | F |  |  |  | ######## | 111-11-1282 | 295 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BCNTwentyFive |  |  | M |  |  |  | 1980-04-02 | 111-11-1283 | 296 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BCNTwentySix |  |  | F |  |  |  | ######## | 111-11-1284 | 297 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BCNTwentySeven |  |  | M |  |  |  | ######## | 111-11-1285 | 298 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BCNTwentyEight |  |  | F |  |  |  | ######## | 111-11-1286 | 299 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BCNTwentyNine |  |  | M |  |  |  | ######## | 111-11-1287 | 300 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BCNThirty |  |  | F |  |  |  | ######## | 111-11-1288 | 301 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BCNThirtyOne |  |  | M |  |  |  | ######## | 111-11-1289 | 302 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BCNThirtyTwo |  |  | F |  |  |  | 1980-04-02 | 111-11-1290 | 303 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BCNThirtyThree |  |  | M |  |  |  | ######## | 111-11-1291 | 304 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
Amanda Osborne | APPOne | AMBOne |  |  | F |  |  |  | ######## | 111-11-1292 | 305 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
Christian Haygood | APPOne | AMBTwo |  |  | M |  |  |  | ######## | 111-11-1293 | 306 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
Lisa Thomas | APPOne | AMBThree |  |  | F |  |  |  | ######## | 111-11-1294 | 307 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | AMBFour |  |  | M |  |  |  | ######## | 111-11-1295 | 308 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | AMBFive |  |  | F |  |  |  | ######## | 111-11-1296 | 309 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | AMBSix |  |  | M |  |  |  | 1980-04-02 | 111-11-1297 | 310 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | AMBSix |  |  | F |  |  |  | ######## | 111-11-1298 | 311 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | AMBEight |  |  | M |  |  |  | ######## | 111-11-1299 | 312 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | AMBNine |  |  | F |  |  |  | ######## | 111-11-1300 | 313 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | AMBTen |  |  | M |  |  |  | ######## | 111-11-1301 | 314 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | AMBEleven |  |  | F |  |  |  | ######## | 111-11-1302 | 315 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | AMBTwelve |  |  | M |  |  |  | ######## | 111-11-1303 | 316 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | AMBThirteen |  |  | F |  |  |  | 1980-04-02 | 111-11-1304 | 317 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | AMBFourteen |  |  | M |  |  |  | ######## | 111-11-1305 | 318 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | AMBFifteen |  |  | F |  |  |  | ######## | 111-11-1306 | 319 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | AMBSixteen |  |  | M |  |  |  | ######## | 111-11-1307 | 320 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | AMBSeventeen |  |  | F |  |  |  | ######## | 111-11-1308 | 321 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | AMBEighteen |  |  | M |  |  |  | ######## | 111-11-1309 | 322 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | AMBNineteen |  |  | F |  |  |  | ######## | 111-11-1310 | 323 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | AMBTwenty |  |  | M |  |  |  | 1980-04-02 | 111-11-1311 | 324 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | AMBTwentyOne |  |  | F |  |  |  | ######## | 111-11-1312 | 325 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | AMBTwentyTwo |  |  | M |  |  |  | ######## | 111-11-1313 | 326 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | AMBTwentyThree |  |  | F |  |  |  | ######## | 111-11-1314 | 327 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | AMBTwentyFour |  |  | M |  |  |  | ######## | 111-11-1315 | 328 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | AMBTwentyFive |  |  | F |  |  |  | ######## | 111-11-1316 | 329 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | AMBTwentySix |  |  | M |  |  |  | ######## | 111-11-1317 | 330 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | AMBTwentySeven |  |  | F |  |  |  | 1980-04-02 | 111-11-1318 | 331 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | AMBTwentyEight |  |  | M |  |  |  | ######## | 111-11-1319 | 332 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | AMBTwentyNine |  |  | F |  |  |  | ######## | 111-11-1320 | 333 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | AMBThirty |  |  | M |  |  |  | ######## | 111-11-1321 | 334 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | AMBThirtyOne |  |  | F |  |  |  | ######## | 111-11-1322 | 335 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | RSHOne |  |  | M |  |  |  | ######## | 111-11-1323 | 336 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | RSHTwo |  |  | F |  |  |  | ######## | 111-11-1324 | 337 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | RSHThree |  |  | M |  |  |  | 1980-04-02 | 111-11-1325 | 338 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | RSHFour |  |  | F |  |  |  | ######## | 111-11-1326 | 339 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | RSHFive |  |  | M |  |  |  | ######## | 111-11-1327 | 340 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | RSHSix |  |  | F |  |  |  | ######## | 111-11-1328 | 341 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | RSHSix |  |  | M |  |  |  | ######## | 111-11-1329 | 342 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | RSHEight |  |  | F |  |  |  | ######## | 111-11-1330 | 343 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | RSHNine |  |  | M |  |  |  | ######## | 111-11-1331 | 344 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | ASAPOne |  |  | F |  |  |  | 1980-04-02 | 111-11-1332 | 345 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | ASAPTwo |  |  | M |  |  |  | ######## | 111-11-1333 | 346 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | ASAPThree |  |  | F |  |  |  | ######## | 111-11-1334 | 347 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | ASAPFour |  |  | M |  |  |  | ######## | 111-11-1335 | 348 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | ASAPFive |  |  | F |  |  |  | ######## | 111-11-1336 | 349 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | ASAPSix |  |  | M |  |  |  | ######## | 111-11-1337 | 350 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | ASAPSix |  |  | F |  |  |  | ######## | 111-11-1338 | 351 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | ASAPEight |  |  | M |  |  |  | 1980-04-02 | 111-11-1339 | 352 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | ASAPNine |  |  | F |  |  |  | ######## | 111-11-1340 | 353 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | ASAPTen |  |  | M |  |  |  | ######## | 111-11-1341 | 354 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | ASAPEleven |  |  | F |  |  |  | ######## | 111-11-1342 | 355 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | ASAPTwelve |  |  | M |  |  |  | ######## | 111-11-1343 | 356 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | ASAPThirteen |  |  | F |  |  |  | ######## | 111-11-1344 | 357 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | ASAPFourteen |  |  | M |  |  |  | ######## | 111-11-1345 | 358 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | ASAPFifteen |  |  | F |  |  |  | 1980-04-02 | 111-11-1346 | 359 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | ASAPSixteen |  |  | M |  |  |  | ######## | 111-11-1347 | 360 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | ASAPSeventeen |  |  | F |  |  |  | ######## | 111-11-1348 | 361 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | ASAPEighteen |  |  | M |  |  |  | ######## | 111-11-1349 | 362 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | ASAPNineteen |  |  | F |  |  |  | ######## | 111-11-1350 | 363 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | ASAPTwenty |  |  | M |  |  |  | ######## | 111-11-1351 | 364 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | ASAPTwentyOne |  |  | F |  |  |  | ######## | 111-11-1352 | 365 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | ASAPTwentyTwo |  |  | M |  |  |  | 1980-04-02 | 111-11-1353 | 366 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | ASAPTwentyThree |  |  | F |  |  |  | ######## | 111-11-1354 | 367 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | ASAPTwentyFour |  |  | M |  |  |  | ######## | 111-11-1355 | 368 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | ASAPTwentyFive |  |  | F |  |  |  | ######## | 111-11-1356 | 369 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | ASAPTwentySix |  |  | M |  |  |  | ######## | 111-11-1357 | 370 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | ASAPTwentySeven |  |  | F |  |  |  | ######## | 111-11-1358 | 371 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | ASAPTwentyEight |  |  | M |  |  |  | ######## | 111-11-1359 | 372 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | ASAPTwentyNine |  |  | F |  |  |  | 1980-04-02 | 111-11-1360 | 373 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | ASAPThirty |  |  | M |  |  |  | ######## | 111-11-1361 | 374 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | ASAPThirtyOne |  |  | F |  |  |  | ######## | 111-11-1362 | 375 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPOne |  |  | M |  |  |  | ######## | 111-11-1363 | 376 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPTwo |  |  | F |  |  |  | ######## | 111-11-1364 | 377 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPThree |  |  | M |  |  |  | ######## | 111-11-1365 | 378 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPFour |  |  | F |  |  |  | ######## | 111-11-1366 | 379 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPFive |  |  | M |  |  |  | 1980-04-02 | 111-11-1367 | 380 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPSix |  |  | F |  |  |  | ######## | 111-11-1368 | 381 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPSix |  |  | M |  |  |  | ######## | 111-11-1369 | 382 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPEight |  |  | F |  |  |  | ######## | 111-11-1370 | 383 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPNine |  |  | M |  |  |  | ######## | 111-11-1371 | 384 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPTen |  |  | F |  |  |  | ######## | 111-11-1372 | 385 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPEleven |  |  | M |  |  |  | ######## | 111-11-1373 | 386 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPTwelve |  |  | F |  |  |  | 1980-04-02 | 111-11-1374 | 387 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPThirteen |  |  | M |  |  |  | ######## | 111-11-1375 | 388 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPFourteen |  |  | F |  |  |  | ######## | 111-11-1376 | 389 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPFifteen |  |  | M |  |  |  | ######## | 111-11-1377 | 390 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPSixteen |  |  | F |  |  |  | ######## | 111-11-1378 | 391 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPSeventeen |  |  | M |  |  |  | ######## | 111-11-1379 | 392 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPEighteen |  |  | F |  |  |  | ######## | 111-11-1380 | 393 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPNineteen |  |  | M |  |  |  | 1980-04-02 | 111-11-1381 | 394 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPTwenty |  |  | F |  |  |  | ######## | 111-11-1382 | 395 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPTwentyOne |  |  | M |  |  |  | ######## | 111-11-1383 | 396 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPTwentyTwo |  |  | F |  |  |  | ######## | 111-11-1384 | 397 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPTwentyThree |  |  | M |  |  |  | ######## | 111-11-1385 | 398 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPTwentyFour |  |  | F |  |  |  | ######## | 111-11-1386 | 399 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPTwentyFive |  |  | M |  |  |  | ######## | 111-11-1387 | 400 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPTwentySix |  |  | F |  |  |  | 1980-04-02 | 111-11-1388 | 401 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPTwentySeven |  |  | M |  |  |  | ######## | 111-11-1389 | 402 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPTwentyEight |  |  | F |  |  |  | ######## | 111-11-1390 | 403 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPTwentyNine |  |  | M |  |  |  | ######## | 111-11-1391 | 404 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPThirty |  |  | F |  |  |  | ######## | 111-11-1392 | 405 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPThirtyOne |  |  | M |  |  |  | ######## | 111-11-1393 | 406 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPThirtyTwo |  |  | F |  |  |  | ######## | 111-11-1394 | 407 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPThirtyThree |  |  | M |  |  |  | 1980-04-02 | 111-11-1395 | 408 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPThirtyFour |  |  | F |  |  |  | ######## | 111-11-1396 | 409 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPThirtyFive |  |  | M |  |  |  | ######## | 111-11-1397 | 410 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPThirtySix |  |  | F |  |  |  | ######## | 111-11-1398 | 411 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPThirtySeven |  |  | M |  |  |  | ######## | 111-11-1399 | 412 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPThirtyEight |  |  | F |  |  |  | ######## | 111-11-1400 | 413 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPThirtyNine |  |  | M |  |  |  | ######## | 111-11-1401 | 414 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPForty |  |  | F |  |  |  | 1980-04-02 | 111-11-1402 | 415 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPFortyOne |  |  | M |  |  |  | ######## | 111-11-1403 | 416 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPFortyTwo |  |  | F |  |  |  | ######## | 111-11-1404 | 417 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPfortyThree |  |  | M |  |  |  | ######## | 111-11-1405 | 418 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPFortyFour |  |  | F |  |  |  | ######## | 111-11-1406 | 419 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPFortyFive |  |  | M |  |  |  | ######## | 111-11-1407 | 420 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPFortySix |  |  | F |  |  |  | ######## | 111-11-1408 | 421 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPFortySeven |  |  | M |  |  |  | 1980-04-02 | 111-11-1409 | 422 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPFortyEight |  |  | F |  |  |  | ######## | 111-11-1410 | 423 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPFortyNine |  |  | M |  |  |  | ######## | 111-11-1411 | 424 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPFifty |  |  | F |  |  |  | ######## | 111-11-1412 | 425 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPFiftyOne |  |  | M |  |  |  | ######## | 111-11-1413 | 426 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPFiftyTwo |  |  | F |  |  |  | ######## | 111-11-1414 | 427 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPFiftyThree |  |  | M |  |  |  | ######## | 111-11-1415 | 428 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPFiftyFour |  |  | F |  |  |  | 1980-04-02 | 111-11-1416 | 429 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPFiftyFive |  |  | M |  |  |  | ######## | 111-11-1417 | 430 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPFiftySix |  |  | F |  |  |  | ######## | 111-11-1418 | 431 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPFiftySeven |  |  | M |  |  |  | ######## | 111-11-1419 | 432 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPFiftyEight |  |  | F |  |  |  | ######## | 111-11-1420 | 433 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPFiftyNine |  |  | M |  |  |  | ######## | 111-11-1421 | 434 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPSixty |  |  | F |  |  |  | ######## | 111-11-1422 | 435 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPSixtyOne |  |  | M |  |  |  | 1980-04-02 | 111-11-1423 | 436 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPSixtyTwo |  |  | F |  |  |  | ######## | 111-11-1424 | 437 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPSixtyThree |  |  | M |  |  |  | ######## | 111-11-1425 | 438 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPSixtyFour |  |  | F |  |  |  | ######## | 111-11-1426 | 439 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPSixtyFive |  |  | M |  |  |  | ######## | 111-11-1427 | 440 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPSixtySix |  |  | F |  |  |  | ######## | 111-11-1428 | 441 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPSixtySeven |  |  | M |  |  |  | ######## | 111-11-1429 | 442 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPSixtyEight |  |  | F |  |  |  | 1980-04-02 | 111-11-1430 | 443 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPSixtyNine |  |  | M |  |  |  | ######## | 111-11-1431 | 444 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPSeventy |  |  | F |  |  |  | ######## | 111-11-1432 | 445 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | IPSeventyOne |  |  | M |  |  |  | ######## | 111-11-1433 | 446 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | IPSeventyTwo |  |  | F |  |  |  | ######## | 111-11-1434 | 447 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BPAMOne |  |  | M |  |  |  | ######## | 111-11-1435 | 448 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BPAMTwo |  |  | F |  |  |  | ######## | 111-11-1436 | 449 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BPAMThree |  |  | M |  |  |  | 1980-04-02 | 111-11-1437 | 450 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BPAMFour |  |  | F |  |  |  | ######## | 111-11-1438 | 451 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BPAMFive |  |  | M |  |  |  | ######## | 111-11-1439 | 452 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BPAMSix |  |  | F |  |  |  | ######## | 111-11-1440 | 453 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BPAMSix |  |  | M |  |  |  | ######## | 111-11-1441 | 454 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com
| APPOne | BPAMEight |  |  | F |  |  |  | ######## | 111-11-1442 | 455 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Single | email@email.com
| APPOne | BPAMNine |  |  | M |  |  |  | ######## | 111-11-1443 | 456 Anywhere Street |  | Gainesville | GA | 30501 | USA | Hall |  |  | 6080000000 | 6080000000 | 6090000000 |  | English |  |  | Married | email@email.com

## PRD Smoke test pivot
Cloud Prod Smoke Test Status | System / Vendor | Count of System / Vendor | Count of Cutover during testing window
Not Testable | 3M HIS Revenue Cycle Solutions (3M CodeFinder, C&RS, C&RS Plus, 360 Encompass System, Medicode) | 1 | 1
| Acumen - Fresenius medical Care | 1
| BD Alaris Pumps | 1 | 1
| Cover My Meds- EPA | 1 | 1
| Encore Quality Management and Reporting | 1 | 1
| GE Airstrip- secure remote access to patient data | 1
| GE Centricity Perinatal (CPN) | 1 | 1
| Guardian Fusion (Guardian Research Network GRN Data Connection) | 1
| ICD- National Cardiovascular Data Registry | 1 | 1
| Imprivata Badge Tap- Test Badge Tap | 1 | 1
| Invita Medical Invita UDI | 1
| Phillips G3 SleepWare | 1 | 1
| Press Ganey | 1
| PRISM-Opthamology | 1 | 1
| Waystar | 1 | 1
Not Testable Total |  | 15 | 10
(blank) | 3M Core Grouper for Claims- Test running claims, check Interconnect trace viewer for errors. | 1 | 1
| AIDA Healthcare | 1 | 1
| Ambry HL7 | 1 | 1
| Aqure (Radiometer America) - Interface Engine | 1 | 1
| Baby 360 by YoMingo | 1 | 1
| Breeze Suite - Interface Engine | 1 | 1
| Capsule Technologies | 1 | 1
| Cardinal Health | 1 | 1
| Care Everywhere | 1 | 1
| Carefeed | 1 | 1
| Carta Healthcare Cartographer | 1
| Change Healthcare- Interconnect Interqual case management | 1 | 1
| Change Healthcare PACS | 1 | 1
| Clinical Skills/ClinicalKey | 1 | 1
| Corepoint | 1 | 1
| CSI ANC LAB | 1 | 1
| Cupid XML to HL7 | 1 | 1
| Cures FHIR- 21st Cures Act | 1 | 1
| Cyracom - Interpreter Services (new integration) | 1 | 1
| DAX Ambient Copilot- FHIR Integration (Nuance) | 1 | 1
| Emdeon / Change Healthcare - Revenue Cycle management | 1 | 1
| Ephiphany | 1 | 1
| Epic Video Client | 1 | 1
| FastPass | 1 | 1
| File Export or FEX | 1 | 1
| Finthrive CRD (interconnect) / CRD - Rapid Retest | 1 | 1
| First Databank- Drug Database | 1 | 1
| Fuse/Signal Radiation Oncology | 1 | 1
| Gastro | 1 | 1
| Get Well - Rounding and Video Client | 1
| Glytec Glucommander- Diabetes care | 1 | 1
| GRITS | 1 | 1
| Haiku/Canto | 1 | 1
| HCI Solutions- Medication Warning | 1 | 1
| IBM Merge Cardio Web | 1 | 1
| Imprivata ConfirmID | 1 | 1
| Insight RX- FHIR | 1 | 1
| Keriton | 1 | 1
| LRS - VPSX | 1 | 1
| MacroHelix | 1
| Mapquest | 1 | 1
| Merge Cardio | 1 | 1
| Merge Heartsuite (Mac Lab) | 1 | 1
| MoveIT | 1
| Murj SMART on FHIR | 1 | 1
| NPLEx | 1
| Nuance Dragon Medical One | 1
| Olympus KE- endoscopy | 1 | 1
| Omnicell | 1 | 1
| Onbase | 1 | 1
| Outgoing Document Interface | 1 | 1
| Outlook Epic Integration | 1 | 1
| Pecos (Dorothy/HomeHealth) | 1 | 1
| PowerScribe | 1 | 1
| Qpath/Telexy | 1 | 1
| QRDA | 1 | 1
| Quest- Beaker ANC LAB results | 1 | 1
| RightFax | 1 | 1
| Rover | 1 | 1
| SEPA- Southeastern Pathology Reports | 1 | 1
| ServiceNow | 1
| SOC Telemed | 1 | 1
| TerminalWorks UniTwain | 1
| Unite Us | 1 | 1
| Varian | 1 | 1
| Weblinks! | 1 | 1
| Willlow Ambulatory | 1
| Kyruus | 1 | 1
| ACR Care Select- Decision support for Radiology | 1 | 1
| Ciox Healthsource | 1 | 1
| CRA Health (previously Volpera)- | 1 | 1
| Dr. First (Surescripts) | 1 | 1
| Imprivata IDG | 1 | 1
| InterQual Medical Review Service for providers (IQ Connect) | 1 | 1
| Intrado (Televox) | 1 | 1
(blank) Total |  | 75 | 66
Post Cutover Test Only | Cognitive Computing Nebula | 1 | 1
| Cosmos | 1 | 1
| CRC- Payment Safe Page | 1 | 1
| Emporos/Merchantsoft | 1 | 1
| E-Signature/Controlled Meds | 1 | 1
| Experian (Credit Card Payment) | 1 | 1
| Experian RTE | 1 | 1
| Happy Together Integrations | 1 | 1
| Phillips Pix IX Webviewer | 1
| Real Time Prescription Benefits (SureScripts) | 1 | 1
| Salucro Payment and Device Integration (MedEpay/Elavon) | 1 | 1
| Seqster Health | 1 | 1
| Steris SPM | 1 | 1
| Surescripts E-Prescribe | 1 | 1
Post Cutover Test Only Total |  | 14 | 13
Grand Total |  | 104 | 89

## Issue Log
Issue Log
ID | Issue Number | Date Raised | Time Raised | Raised By | Issue Owner | Runbook Task ID | Issue Severity | Issue Description | Actions Taken | Action By | Issue Status | Date Closed | Time Closed | Closed By
1 |  | 5/28/2025 |  | Marylynn O'Reilly |  |  |  | Glucommander did not launch. SmartClickV3 experienced an unexpected problem causing your login to fail. SmartClickV3 unexpected exception processing Landing page. Error: G-GC-S-1-000006. System.IO.DirectoryNotFoundException: Could not find a part of the path 'D:\inetpub\wwwroot\GSENT.1689-t01.glytecenterprise.com.3512\csharp\Glucommander\Views\SMARTonFHIR\Landing\LandingError.cshtml' | Firewall updated by Ajay on 6/2/2025 | Ajay | Closed
2 |  | 5/28/2025 |  | Lisa Turner, Amanda Osborne, Christian Haygood |  |  |  | When attempting to log into Haiku app as FAMMD I got message, "Login Failure Communication with the server timed out. Seek assistance from an administrator if the problem persists. Code: TimedOut. | Firewall updated by Ajay on 6/2/2025 | Ajay | Closed
3 |  | 5/28/2025 |  | Nicole Benson |  |  |  | Willow - Insight RX - getting 504 Gateway Time-out error. | Firewall updated by Ajay on 6/2/2025 | Ajay | Closed
4 |  | 5/28/2025 |  | Ashley Tipton |  |  |  | The new teleneuro SOC link for BRS is not working. The new build was migrated Monday and confirmed working in regular PRD. | this works as expected after another refresh |  | Closed
5 |  | 5/28/2025 |  | Ram Chimpudi |  |  |  | BD Alaris Pumps need IPs swung internally. Add this to cutover runbook and find owner. vmasalariscce01 - 172.16.74.144 - CCE TEST vmasalariscce03 - 172.16.74.146 - CCE PROD | BD Alaris system is not a production system |  | Closed
6 |  | 5/28/2025 |  | Scott Sanderson |  |  |  | Login coming back to on-prem AD servers, causing excessive login times | Still digging but not an issue to testing on 6/17 |  | Closed
7 |  | 5/28/2025 |  | Brett Kennedy |  |  |  | Change Healthcare/Interqual 500 https://teams.microsoft.com/l/message/19:meeting_N2NiNzE2YWQtMTFhOC00YzY2LWI1NDMtN2NkM2M5NzE2Yjk3@thread.v2/1748454683746?context=%7B%22contextType%22%3A%22chat%22%7D | Firewall updated by Ajay on 6/2/2025 | Ajay | Closed
8 |  | 5/28/2025 |  | Bradley Gantt |  |  |  | Merge Cardio image links are prompting for user credentials. Normally it passes through automatically. https://vmascardcastst1.nghs.com/vericis_web/studyreviewdefault.asp?PID=%PATID% | SLG 10055493 opened with Epic Checked link in Hyperdrive TST on-prem and there is no prompt for user credentials |  | Closed
9 |  | 5/28/2025 |  | Bradley Gantt |  |  |  | ECG image links are prompting for user credentials. Normally it passes through automatically. https://vmasepiphtest3.nghs.com/webapi/webtrust2.php?wt_username=%CRYPTSTR;;;;;;URL% | SLG 10055493 opened with Epic Checked link in Hyperdrive TST on-prem and there is no prompt for user credentials |  | Closed |  |  |  | Trouble
10 |  | 5/28/2025 |  | Ram Chimpudi |  |  |  | GRITS Histroy Query - AIP-640320 - Msg transmission failed on Interconnect. | Firewall updated by Ajay on 6/2/2025 | Ajay | Closed
11 |  | 5/28/2025 |  | Ram Chimpudi |  |  |  | ODI queue type - AIP- 640100 and 640102 timed out | was fixed on-Prem environment . its ready for -AWS testing on 6/17 |  | Closed
12 |  |  |  | Ron |  |  |  | Internal Split DNS needs to be fixed before next run | we should turn Exsisiting DNS A records for split DNS of the urls to Cnames and move them up a level like we did for external should be trackable tasks |  | Closed
13 |  |  |  | Steve |  |  |  | Logs not going to DFS | need to investage why should be trackable tasks | STeve R | Closed
14 |  |  |  | Chinmay/ David |  |  |  | VPNs not listed in Routes and do not have conformation of VPNS are even in place | need to investage and impliment should be trackable tasks | Chinmay | Closed
15 |  |  |  | Shawn |  |  |  | Added 5 high ports need to document | need to make sure they are documented | Shawn | Closed
16 |  | 6/19/25 |  | Nicole Benson |  |  |  | Willow - Insight RX - getting error 404 - File or directory not found |  | STeve R | Closed
17 |  | 6/19/25 |  | Erin Cordova |  |  | Medium | Change Healthcare/Interqual Connect - I'm able to launch Interqual from Epic without issues, but info is not filing back from Interqual into Epic. Per vendor, they use the SMART FHIR url to return into into Epic. Non-prd file-back URL = https://wptst.nghs.com/iqconnect-tst/api/epic/2019/ManagedCare/UM/FileInterQualReview INTERQUAL CONNECT MEDICAL REVIEW SERVICE FOR PROVIDERS [FDI 100074] | moved its own Interconnect instance (like the on-prem environment), rather than having it consolidated on the webservice instance. | STeve R | Closed
18 |  | 6/19/25 |  | Earl Turner |  |  | Medium | Surescripts doesn't currently work from cloud. Surescripts did also just take their service to the cloud yesterday, which may be impacting our testing today. | Earl and Amanda investigating Fixed as of 8/4 |  | Closed
19 |  | 6/19/25 |  | Shelvia Stewart |  |  | Low | Unknown issuer: clinicalkey-nursing has no EHR configuration uploaded for https://wptst.nghs.com/fhir-tst/api/FHIR/DSTU2 Same behavior as on-prem | This is working as expected. AIDA dashboard launches post refresh | Shelvia | Open
20 |  |  |  | Tomel, Amanda Osborne |  |  | Low | Dragon mics don't work, button doesn't turn on to record. | Only really need to be tested for upgrade, but should not be neglected. |  | Open
|  |  |  | Rick Edwards, Kevin McBride |  |  | Medium | Radiant Warp Drive items listed in Peripheral Testing unable to be tested until cnames get applied | Once cnames are applied as part of permanent cutover, Rick will be looking to test these |  | Open
|  |  |  | Matt Fowler |  |  | Low | Cloud citrix storefront inactivity timeout is much shorter than on-prem - 30min vs 1hr | Christopher Crisson setting time next week to troubleshoot surpressing the warning https://nghs.service-now.com/u_incident_task.do?sys_id=8e26efc433aea6d0d3bd3ec9bd5c7b9a&sysparm_record_target=u_incident_task&sysparm_record_row=1&sysparm_record_rows=1&sysparm_record_list=u_incident%3D6165a78033aea6d0d3bd3ec9bd5c7bd6%5EORDERBYnumber | Christopher Crisson | Closed
|  |  |  | Peter Dcosta |  |  | Medium | native Epic exports fail in cloud TST, works in on-prem |  | STeve R | Open
|  | 9/9/25 |  | Drew Gardner |  |  |  | 360 Encompass FHIR Communication Client "Step 1 did not provide iss and launch"- error persists after previous troubleshooting Getting same "Step 3" invalid_grant failed to redeem a launch token for an authoraization code" error - 9/25 | Hannah is working with Care Everywhere TS to resolve phonebooking. Phonebooking fixed but still running into the issue described. Confirmed same behavior on both published app and cloud coders desktop. | Jason Deaver | Closed
|  | 9/9/25 |  | Lissette Alonso |  |  |  | Glucommander FHIR blocking "Your SmartClick V3 login failed because the EMR reported an error invalid_grant" 9/25 | Hannah is working with Care Everywhere TS to resolve phonebooking. Phonebooking fixed. Invalid OAuth 2.0 request - issue persists 9/16 Converting this to Post Cutover Test only |  | Closed
|  | 9/9/25 |  | Erin Cordova |  |  |  | Interqual 403 access forbidden FHIR After phonebook changes, this changed to a 500 error - persists as of 9/16, 9/25 | Hannah is working with Care Everywhere TS to resolve phonebooking. Phonebooking fixed. The 500 error looks similar to the issue we had in TST where firewall rule needed to be updated by Ajay. Authorization code is getting rejected | Jason Deaver | Closed | 9/25/25 | 4:13 PM | Erin Cordova
|  | 9/9/25 |  | Nicole Benson |  |  | High | InsightRX "Error: No Org found loading" - issue persists 9/16 | Hannah is working with Care Everywhere TS to resolve phonebooking. Phonebooking fixed. Now running into "Request failed with status code 500" Successful test after FHIR issues start to be resolved. | Jason Deaver | Closed | 2025-09-23 | 4:20 | Nicole Benson
|  | 9/9/25 |  | Chris Crisson |  |  |  | Issue with synchronization between storefront servers | Chris is troubleshooting with the Citrix team |  | Closed | 2025-09-18 | 9:00AM | Chris Crisson
|  | 9/9/25 |  | Joshua Small |  |  |  | Experian Payment page "Error getting payment session data from Epic" | Doesn't have a test system, marked for testing Post-Cutover |  | Closed
|  | 9/9/25 |  | Matt Fowler, Mitchell Hawes |  |  |  | Unable to LDAP to EMPs/SERs needed for workflow testing | Troubleshooting with Mitchell and Hannah Hannah had to disable LDAP because something happened with the E0A import this morning. |  | Closed
|  | 9/9/25 |  | Ram Chimpudi |  |  |  | Ports 33317 need to be opened for Cardiology | Working with Jameson to get this opened | Jameson | Closed
|  | 9/11/25 |  | Ashley Tipton |  |  |  | SOC Telemed Corepoint doesn't launch - just a white screen - FHIR - issue persists as of 9/16, 9/25 Able to send data now, but no data comes back in. Mitzi is chatting with their support today - 9/26 | Troubleshooting with Ram - some routing needs to be adjusted by Steve - should we coordinate all of these to be fixed before next session? | Steve Reagan | Open
|  | 9/11/25 |  | Donna Kinslow, Amanda Osborne |  |  |  | CRA Health (Volpera) Corepoint - Not returning data - FHIR | Troubleshooting with Ram - some routing needs to be adjusted by Steve - should we coordinate all of these to be fixed before next session? | Steve Reagan | Open
|  | 9/12/25 |  | Nicole Benson |  |  |  | Cloud TST InsightRX - "Epic OAuth sever responded with: undefined :: URI..." | attempting again today (9/12) and checking logs Nicole is reaching out to InsightRX support | Steve Reagan | Closed | 2025-09-16 | 1140 | NB - it is currently working
|  | 9/12/25 |  | Lisa Fiorucci |  |  | High | Unspecified Rover disruptions to the training team in TST ClinDoc | Need to chat with Peter Dcosta when he's back on Tues 9/16 Steve and Mitchell are working on getting Peter the proper config file for PRD 9/18 ClinDoc workflows test properly, conducted flowsheets, meds, orders, patient education,, notes 9/25 | Steve Reagan | Closed | 2025-09-25 |  | Peter Dcosta
|  | 9/15/25 |  | Chris Chumbley |  |  | Medium | Zebra printers from thin clients don't work | Steve investigating | Steve Reagan | Open
|  | 9/15/25 |  | Chris Chumbley |  |  | Medium | Scanning doesn't work out of epic PRD thin client | Works as expected from TST and Scandall Pro, just not from within thin client Cloud PRD | Tomel Morrison | Closed
|  | 9/15/25 |  | Chris Chumbley |  |  | Low | Signature pads don't work out of epic thin client | Appears broken on image, Citrix team investigating | Tomel Morrison | Closed
|  | 9/16/25 |  | Earl Turner |  |  | Medium | Willow AMB not properly querying patient data. LC is working correctly in this manor. | Jason made a change and this is now resolved | Jason Deaver | Closed
|  | 9/16/25 |  | Shelvia Stewart |  |  | Low | AIDA Dashboard gets stuck on loading, no other errors - FHIR Issue New error "invalid_grant failed to redeem a launch token for an authorization code" - 9/25 |  | Jason Deaver | Closed
|  | 9/16/25 |  | Chris Chumbley |  |  | Medium | Sectra PACS running into networking issue with VPN tunnel | David is working with Ron on the routing issue | Ron Metzger | Open
|  | 9/18/25 |  | Lisa Thomas |  |  | Medium | Barcode scanner for Ambulatory workflows silently fails in Cloud PRD Smoke Test, from thin client desktop app and published app. Works as expected in TST. | Engaging citrix team | Tomel Morrison | Open
|  | 9/18/25 |  | Mitzi Donaldson |  |  | Low | Dragon mic app isn't able to find the attached Dragon mic device. We had a successful test on the Dragon device, earlier in the day, but the difference here is that Mitzi started her test with the mobile app as the mic, which also worked. Still an issue 9/25 | Engaging citrix team | Tomel Morrison | Open
|  | 9/25/25 |  | Jennifer Horn |  |  | Low | Intrado Televox not getting a message | Jason Deaver | Jason Deaver | Closed | 2025-09-25
|  | 9/25/25 |  | Shelvia Stewart |  |  | Low | Clinical Skills errors: "Unknown issuer: clinicalSkillsProd has no EHR configuration for https://wptst.nghs.com/fhir-tst/api/FHIR/DSTU2" |  | Jason Deaver | Closed

## Dry Run 2 Values
Count of Dry Run 2 Status | Dry Run 2 Fail
System / Vendor | Fail | Not Testable | Pass | (blank) | Post Cutover Test Only | Grand Total
3M Core Grouper for Claims- Test running claims, check Interconnect trace viewer for errors.
3M HIS Revenue Cycle Solutions (3M CodeFinder, C&RS, C&RS Plus, 360 Encompass System, Medicode) |  | 1 |  |  |  | 1
Acumen - Fresenius medical Care |  | 1 |  |  |  | 1
AIDA Healthcare |  |  | 1 |  |  | 1
Ambry HL7
Aqure (Radiometer America) - Interface Engine |  |  | 1 |  |  | 1
Baby 360 by YoMingo
BD Alaris Pumps |  | 1 |  |  |  | 1
Breeze Suite - Interface Engine |  |  | 1 |  |  | 1
Capsule Technologies
Cardinal Health |  | 1 |  |  |  | 1
Care Everywhere |  |  | 1 |  |  | 1
Carefeed |  |  | 1 |  |  | 1
Carta Healthcare Cartographer |  | 1 |  |  |  | 1
Change Healthcare- Interconnect Interqual case management | 1 |  |  |  |  | 1
Change Healthcare PACS
Clinical Skills/ClinicalKey | 1 |  |  |  |  | 1
Cognitive Computing Nebula |  |  |  |  | 1 | 1
Corepoint
Cosmos |  |  |  |  | 1 | 1
Cover My Meds- EPA |  | 1 |  |  |  | 1
CRC- Payment Safe Page |  |  |  |  | 1 | 1
CSI ANC LAB |  |  | 1 |  |  | 1
Cupid XML to HL7 |  |  | 1 |  |  | 1
Cures FHIR- 21st Cures Act |  | 1 |  |  |  | 1
Cyracom - Interpreter Services (new integration) |  | 1 |  |  |  | 1
DAX Ambient Copilot- FHIR Integration (Nuance) |  |  | 1 |  |  | 1
Emdeon / Change Healthcare - Revenue Cycle management
Emporos/Merchantsoft |  |  |  |  | 1 | 1
Encore Quality Management and Reporting |  | 1 |  |  |  | 1
Ephiphany |  |  | 1 |  |  | 1
Epic Video Client
E-Signature/Controlled Meds |  |  |  |  | 1 | 1
Experian (Credit Card Payment) |  | 1 |  |  |  | 1
Experian RTE |  | 1 |  |  |  | 1
FastPass |  |  | 1 |  |  | 1
File Export or FEX |  | 1 |  |  |  | 1
Finthrive CRD (interconnect) / CRD - Rapid Retest |  | 1 |  |  |  | 1
First Databank- Drug Database
Fuse/Signal Radiation Oncology
Gastro |  |  | 1 |  |  | 1
GE Airstrip- secure remote access to patient data |  | 1 |  |  |  | 1
GE Centricity Perinatal (CPN) |  | 1 |  |  |  | 1
Get Well - Rounding and Video Client |  |  | 1 |  |  | 1
Glytec Glucommander- Diabetes care |  |  | 1 |  |  | 1
GRITS |  |  | 1 |  |  | 1
Guardian Fusion (Guardian Research Network GRN Data Connection) |  | 1 |  |  |  | 1
Haiku/Canto |  |  | 1 |  |  | 1
Happy Together Integrations |  |  | 1 |  |  | 1
HCI Solutions- Medication Warning |  | 1 |  |  |  | 1
IBM Merge Cardio Web | 1 |  |  |  |  | 1
ICD- National Cardiovascular Data Registry |  | 1 |  |  |  | 1
Imprivata Badge Tap- Test Badge Tap |  | 1 |  |  |  | 1
Imprivata ConfirmID |  |  | 1 |  |  | 1
Insight RX- FHIR |  |  | 1 |  |  | 1
Invita Medical Invita UDI |  | 1 |  |  |  | 1
Keriton
LRS - VPSX
MacroHelix |  |  | 1 |  |  | 1
Mapquest |  |  | 1 |  |  | 1
Merge Cardio | 1 |  |  |  |  | 1
Merge Heartsuite (Mac Lab)
MoveIT |  |  | 1 |  |  | 1
Murj SMART on FHIR |  | 1 |  |  |  | 1
NPLEx |  | 1 |  |  |  | 1
Nuance Dragon Medical One |  | 1 |  |  |  | 1
Olympus KE- endoscopy
Omnicell
Onbase
Outgoing Document Interface |  |  | 1 |  |  | 1
Outlook Epic Integration
Pecos (Dorothy/HomeHealth) |  |  | 1 |  |  | 1
Phillips G3 SleepWare |  | 1 |  |  |  | 1
Phillips Pix IX Webviewer |  | 1 |  |  |  | 1
PowerScribe |  |  | 1 |  |  | 1
Press Ganey |  | 1 |  |  |  | 1
PRISM-Opthamology |  | 1 |  |  |  | 1
Qpath/Telexy
QRDA |  |  | 1 |  |  | 1
Quest- Beaker ANC LAB results |  |  | 1 |  |  | 1
Real Time Prescription Benefits (SureScripts) | 1 |  |  |  |  | 1
RightFax |  |  | 1 |  |  | 1
Rover |  |  | 1 |  |  | 1
Salucro Payment and Device Integration (MedEpay/Elavon) |  | 1 |  |  |  | 1
SEPA- Southeastern Pathology Reports |  |  | 1 |  |  | 1
Seqster Health |  | 1 |  |  |  | 1
ServiceNow
SOC Telemed |  |  | 1 |  |  | 1
Steris SPM |  | 1 |  |  |  | 1
Surescripts E-Prescribe | 1 |  |  |  |  | 1
TerminalWorks UniTwain |  | 1 |  |  |  | 1
Unite Us |  |  | 1 |  |  | 1
Varian
Waystar |  | 1 |  |  |  | 1
Weblinks! |  |  | 1 |  |  | 1
Willlow Ambulatory |  | 1 |  |  |  | 1
Kyruus
ACR Care Select- Decision support for Radiology
Ciox Healthsource
CRA Health (previously Volpera)-
Dr. First (Surescripts)
Imprivata IDG |  |  | 1 |  |  | 1
InterQual Medical Review Service for providers (IQ Connect) | 1 |  |  |  |  | 1
Intrado (Televox) |  |  | 1 |  |  | 1
Grand Total | 7 | 33 | 34 |  | 5 | 79

## Apps still to test by team
Team | Manager(s) | Reps for Rd2 | Check-in for Rd2? | Apps | Tested?
ADM GENERAL | John Hale | James Choi, Kyle Hriczo | TRUE | Clinical Skills | TRUE
ANC CARDIOLOGY | Tina Chapman | Ashlee Shiffer(Cupid), Bradley Gantt, Brittney Nix | TRUE | IBM Merge Cardio Web | TRUE
|  |  |  | Merge Heartsuite | TRUE
|  |  |  | Merge Cardio | TRUE
|  |  |  | Ephiphany | TRUE
|  |  |  | Cupid XML to HL7 | TRUE
ANC LAB | Kevin McNeil | Darshna Patel, Nelson Dowling | TRUE | Ambry HL7 | TRUE
|  |  |  | CSI ANC LAB | TRUE
|  |  |  | Quest- Beaker ANC LAB results | TRUE
|  |  |  | Rover | TRUE
CAT AMBULATORY | Mark Thomas | Lisa Thomas, Christian Haygood, Amanda Osborne | TRUE | GRITS | TRUE
|  |  |  | Haiku/Canto | TRUE
|  |  |  | Happy Together Integrations | TRUE
|  |  |  | Seqster Health | TRUE
|  |  |  | Murj SMART on FHIR | TRUE
CAT INPATIENT | Cindy Sullivan, Mitzi Donaldson | Marylynn O'Reilly(ClinDoc), Shelvia Stewart | TRUE | DAX Ambient Copilot- FHIR Integration (Nuance) | TRUE
|  |  |  | Glytec Glucommander- Diabetes care | TRUE
|  |  |  | AIDA Healthcare | TRUE
|  |  |  | File Export or FEX | TRUE
CAT PHARMACY | Cindy Sullivan | Nicole Benson, Earl Turner, Amanda Osborne | TRUE | Emporos/Merchantsoft | FALSE
|  |  |  | MacroHelix | TRUE
|  |  |  | Real Time Prescription Benefits (SureScripts) | TRUE
|  |  |  | Insight RX- FHIR | TRUE
|  |  |  | Surescripts E-Prescribe | TRUE
DATA SERVICES | Martha Hernandez Garcia | Mark Pawloski, Benjamin Simmons | TRUE | MoveIT | TRUE
ECSA | Scott Sanderson | Steve Reagan | TRUE | RightFax | TRUE
HOSPICE | Cindy Sullivan | Casey Barron | TRUE | Pecos (Dorothy/HomeHealth) | TRUE
INTERFACES | Chris Wright | Ram Chimpudi, Jennifer Bailey | TRUE | Acumen - Fresenius medical Care | TRUE
|  |  |  | Carefeed | TRUE
|  |  |  | Gastro | TRUE
|  |  |  | SEPA- Southeastern Pathology Reports | TRUE
Physical Security | Antonio Davis | Paul DeLeon | TRUE | FastPass | TRUE
Population Health | Frankie Grant | Shreya Kotak | TRUE | QRDA | TRUE
|  |  |  | Unite Us | TRUE
REV HIM | Michael McNeilly | Tyjuane Albright | TRUE | Outgoing Document Interface | TRUE
REV PATIENT ACCESS | Tamara Bethel-Williams | Brandi Gaskin (Cadence), Erin Cordova (PtAccess). Joshua Small, Brett Kennedy | TRUE | Change Healthcare- Interconnect Interqual case management | TRUE
|  |  |  | Emdeon / Change Healthcare - Revenue Cycle management | TRUE
|  |  |  | CRC- Payment Safe Page | TRUE
|  |  |  | Experian (Credit Card Payment) | TRUE
|  |  |  | Experian RTE | TRUE
|  |  |  | InterQual Medical Review Service for providers (IQ Connect) | TRUE
|  |  |  | Intrado REV PATIENT ACCESS SMS / Televox SMS used by Mychart | TRUE
|  |  |  | Get Well - Rounding Video Client | TRUE
|  |  |  | TerminalWorks UniTwain | TRUE
Willow | Mark Thomas | Earl Turner | TRUE | Willlow Ambulatory | FALSE
|  |  |  | Omnicell | TRUE

## Inputs
Roles | Status | Teams | Organization | Names | Service Now Teams
Ambulatory | Pass | Ambulatory | NGHS | Test User | ANC RADIOLOGY
Analytics | Fail | Analytics |  |  | CAT PHARMACY
Beacon | No Test System | Beacon |  |  | ADM GENERAL
Beaker | Post Cutover Test Only | Beaker |  |  | AMB ONCOLOGY - RESEARCH
Cadence | FHIR Issue | Cadence |  |  | ITS FIELD SERVICES
ClinDoc |  | ClinDoc |  |  | REV HIM
Data Courier |  | Data Courier |  |  | LAB SYSTEM COORDINATORS
DoCo- Dorothy |  | DoCo- Dorothy |  |  | REV REVENUE CYCLE
ECSA |  | ECSA |  |  | ANC CARDIOLOGY \ ECSA
HIM |  | HIM |  |  | CAT INPATIENT
Hospital Billing |  | Hospital Billing |  |  | ITS SYSTEM ARCHITECTURE
Interfaces |  | Interfaces |  | Chris Wright | ITS BUSINESS INTELLIGENCE
MyChart |  | MyChart |  |  | ITS ENTERPRISE ARCHITECTURE
Orders |  | Orders |  |  | REV PATIENT ACCESS
PACS |  | PACS |  |  | ITS TELECOM
ANC CARDIOLOGY
ANC LAB
BIOMEDICAL SERVICES
CAT - MYCHART
CAT - ONC - RESEARCH
CAT AMBULATORY
CAT HOSPICE
CAT POPULATION HEALTH AND QUALITY
ITS ADMIN TRIAGE
ITS AUDIO VISUAL (AV)
ITS BI REV CYCLE - FINANCE
ITS BI WORKDAY
ITS CLINICAL APPLICATION TEAM TRIAGE
ITS COMMUNITY OUTREACH
ITS CONNECT - SHAREPOINT
ITS DATA SERVICES
ITS ENTERPRISE PLATFORMS
ITS ENVIRONMENTS
ITS INFORMATION SECURITY
ITS INTERFACES
ITS NETWORK SERVICES
ITS SYSTEMS ENGINEERING
ITS WORKFLOW
Analysts \ ECSA
CAT AMBULATORY \ ECSA
CAT AMBULATORY \ ANC RADIOLOGY\ ECSA
REV HIM \ ECSA
CAT INPATIENT \ ECSA

## Devices Models
xrxversalinkb
ZebraZD410
ZebraZT410-203dpiZPL_Rotate
HPLJM402n
HPLJM452nw
Xerox4260
HP
HPLJM401n
Xerox4250
xrxphsr
HPM402n
HPM401dn
HPM252dw
Xerox3635MFP
101HIMPC001_SECURECAPTURE
HPLJM401
XeroxWC4260
ZebraGK420d-GapNotch_Rotate
HPLJM251nw
xrx
JetDirect
HpLJ-2300
HPLJ-M401n
HPColorLJ-M251
XeroxPhaser3635
Xerox7855i
HPLJM451nw
Xerox4265
HPLJM252
Xerox3635
willowxrxversalinkb
ZebraGX420d
XeroxWC5855
ZebraGX420d-GapNotch_Rotate
ZebraZT410-203dpi-3.5x1_Rotate
Xerox7855
Xerox6655
HPLJP3005
HPLJM401dn
HPLJ-M402n
HPLJ-M402
HPLJ-M401
XeroxWC5845
Xerox5845
HPLJP2035n
HPLJ401
HPLJ400
HPLJP2055dn
HPLJM551
HPLJ9050
PrintMateAS450
ZebraQLn220
Xerox
ZebraGX430T-300dpi
HPM401n
HPLJ4050
HPJetDirect
HPLJ4225
XeroxMFP3635
HPLJM252dw
ZebraZT410-300dpi_Rotate
HPLJ402n
XeroxWC4265
XeroxWC7855i
ZebraZT510-203dpiZPL_Rotate
Xerox3655
WC3655
WC4265
Xerox3665
XeroxWC3665
versalinkb
HPM452nw
HPLJM602
HPLJM402
Xerox4255
KonicaMinolta
ZebraZT410-300dpi-3.5x1_Rotate
XR
XeroxWC4250
HPLJ-M602
XeroxWC5945
HPLJ4050n
HPLJ4250n
HPColorLJ-M402n
HPColorLJ-M452nw
HPLJ-4200
HPLJ-4100
XeroxWC3655
Dell5330dn
Dell2330dn
HPM601
XeroxWC3655X
HPLJ-P2055dn
Xerox3655i
XeroxB405
HPCOLORLJM252dw
HPLJ4250
HPLJM651
Xerox3655X
Dell
HPLJ-402n
HP1525nw
HPLJP4014
HPColorLJM451nw
Dell1720dn
HPColorLJ-M252dw
HPLJ-M402dn
HPLJ-M401dn
HPLJ-2100n
HPLJ-4250
HPLJM452
HPLJ4014
XeroxWC7845
HPM254DW
HPLJ600
HPLJ401n
HPLJ806
Xerox9303
Xerox7535
XeroxWC3655i
404HIMPC001_SECURECAPTURE
404HIMPC002_SECURECAPTURE
404HIMPC003_SECURECAPTURE
404HIMPC004_SECURECAPTURE
404HIMPC005_SECURECAPTURE
404HIMPC006_SECURECAPTURE
404HIMPC007_SECURECAPTURE
404HIMPC008_SECURECAPTURE
404HIMPC010_SECURECAPTURE
404HIMPC011_SECURECAPTURE
404HIMPC012_SECURECAPTURE
404HIMPC014_SECURECAPTURE
404HIMPC015_SECURECAPTURE
404HIMPC026_SECURECAPTURE
404HIMPC027_SECURECAPTURE
404HIMPC029_SECURECAPTURE
404HIMPC045_SECURECAPTURE
404RBLPC091_SECURECAPTURE
404RBLPC102_SECURECAPTURE
Brother
Savin
ZebraZT410
CANON
SAVANE
KYOCERA
RICOH
XeroxWC7855
Xerox5945
SECURECAPTURE
Topaz T-LBK460 BSB-R
Ambir ID Scanner DS687-3
Ambir ID Scanner DS687-5 Pro
Honeywell Barcode 1952HHD
Fijitsu Document Scanner Fi-7160 and 8170
Nunance Powermic Version 2/3/4
Microsoft LifeCam HD3000
Creative Live Cam HD Vf0770
Logitech WebCam Brio
Logitech UVC c270